Amazon Alexa

EDS Migration Analysis Report

Comprehensive Site Inventory & Edge Delivery Services Migration Scoping

Date: May 4, 2026

Consumer: https://alexa.amazon.com

Developer: https://developer.amazon.com/en-US/alexa

# Executive Summary

The Amazon Alexa web presence spans three distinct domains: the consumer portal (alexa.amazon.com), the developer portal (developer.amazon.com/en-US/alexa), and Amazon.com product pages. The consumer portal is a lightweight marketing/sign-in gateway (~5-8 pages). The developer portal is a comprehensive developer documentation and community hub (~120+ pages). Amazon.com commerce pages are NOT viable for EDS migration.

Key Metrics:

• ~120-144 total migratable pages

• 38 unique UI blocks/components

• 15 page templates

• 18 third-party integrations

• 16-24 forms

• ~170-235 digital assets

• 9+ language versions

• Estimated effort: 273 person-days (~20 weeks, 3-person team)

• Estimated cost: ~$455,000

# 1. Current Technology Stack

| Layer | Technology | Evidence |
| --- | --- | --- |
| Platform (Consumer) | Amazon proprietary (server-rendered) | m.media-amazon.com CDN, fls-na tracking |
| Platform (Developer) | AWS-based CMS/Portal Framework | CloudFront CDN (ds6yc8t7pnx74.cloudfront.net) |
| Frontend | Vanilla HTML/CSS/JS + proprietary framework | No React/Vue/Angular detected |
| CDN | Amazon CloudFront | CloudFront distribution domains |
| Media | Amazon Media Services | m.media-amazon.com |
| Video | Embedded proprietary player | Video carousel on consumer pages |
| Search | Custom CloudFront-indexed search | Search data endpoint on CloudFront |
| Forms | Qualtrics (surveys/newsletter) | Newsletter and feedback forms |
| Auth | Amazon SSO / OpenID | signin gateway, OpenID parameters |
| Analytics | Amazon internal (fls-na pixel) | Batch pixel processing |
| i18n | URL path-based + selector | 9+ languages |
| Code Hosting | GitHub | github.com/alexa |
| Learning | Sana LMS (external) | alexa.sana.ai |

## 1.1 Pages by Thematic Breakdown

| Theme/Section | Pages (Est.) | Type |
| --- | --- | --- |
| Consumer Landing (Alexa+) | 5-8 | Marketing |
| Developer Hub/Homepage | 3-5 | Marketing/Portal |
| Alexa Skills Kit | 15-20 | Product/Documentation |
| Device Makers | 10-12 | Product/Documentation |
| Solution Providers | 8-10 | Directory/Marketing |
| Alexa AI / SDKs | 5-8 | Product/Technical |
| Alexa Smart Properties | 8-10 | Vertical Marketing |
| Programs (Startups/Fund/Prize) | 12-15 | Program/Community |
| Branding Guidelines | 6-8 | Asset/Guidelines |
| Training & Workshops | 5-8 | Educational |
| Blog Hub/Categories | 8-10 | Content/Blog |
| Champions/Community | 3-5 | Community |
| Voice Interoperability | 3-5 | Technical/Standards |
| Documentation Hubs | 10-12 | Documentation |
| Legal/Support | 5-8 | Administrative |
| TOTAL (Migratable) | ~108-144 |  |

## 1.2 Static vs Dynamic Data Design

| Category | Pages | % | Description |
| --- | --- | --- | --- |
| Static/Marketing | 75-85 | 60% | Product, landing, program, guidelines pages |
| Semi-Dynamic | 25-35 | 25% | Blog, champions, partner directories |
| Dynamic/Tool-Based | 15-20 | 15% | Console, search, training, forums |
| TOTAL | ~120 | 100% |  |

## 1.3 Design System Analysis

Developer Portal uses a consistent proprietary design system:

• Modular card-based layouts with consistent spacing

• Global navigation with multi-level dropdowns

• CloudFront-hosted static assets and shared icon library

• Consistent footer pattern (Resources, Support, Legal, Social, Language)

• Blue/dark (Amazon #232F3E) palette with orange accents

• Newsletter signup component ('Voice Mail') across pages

Consumer Portal: Minimal design system with progressive disclosure, alternating layouts, and video carousel.

Gap: No formal documented web UI design system exists (only Alexa product branding guidelines).

# 2. Templates Inventory

| # | Template Name | Complexity | Reasoning | Example URL |
| --- | --- | --- | --- | --- |
| 1 | Consumer Landing | Medium | Hero + feature grid + video carousel + auth | alexa.amazon.com |
| 2 | Developer Portal Hub | Medium | Multi-level nav, hero, action cards, newsletter | developer.amazon.com/en-US/alexa |
| 3 | Product/SKU Marketing | Medium | Hero, value props, case studies, testimonials | developer.amazon.com/en-US/alexa/alexa-skills-kit |
| 4 | Technical Product Detail | Medium | Breadcrumb, diagram, features, changelog | .../alexa-skills-kit/get-deeper/custom-skills |
| 5 | Vertical Marketing | Medium | Vertical cards, customer success carousel | .../alexa-smart-properties |
| 6 | Program/Community | Medium | Vision, portfolio grid, news cards | .../alexa-startups |
| 7 | Getting Started/Tutorial | Medium | Learning paths, course cards, video embeds | .../alexa-skills-kit/start |
| 8 | Training Catalog | Low | Course cards with duration, launch buttons | .../trainings_and_workshops |
| 9 | People/Champions | Medium | Geographic tabs, profile grid | .../alexa/champions |
| 10 | Blog Hub | Low | Category cards, 4-column grid | .../blogs/alexa |
| 11 | Brand Guidelines | Medium | Left sidebar, expandable sections | .../branding/alexa-guidelines |
| 12 | Solution Provider Directory | Medium | Category overview, provider cards | .../solution-providers |
| 13 | Feature Updates/Changelog | Low | Release types, locale table | .../new/feature-updates |
| 14 | AI/SDK Showcase | High | Hero, SDK cards, video cases, testimonials | .../alexa-ai |
| 15 | Standards/Initiative | Medium | Video hero, mission pillars, resources | .../voice-interoperability |

# 3. Blocks/Components Catalog

## 3.1 Navigation & Layout

| # | Block | Complexity | Description | EDS Standard | Backend | Edge Worker | UI Ext |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Global Dev Nav | High | Multi-level dropdown, 60+ links, lang selector | Custom nav | No | No | Medium |
| 2 | Consumer Nav | Low | Simple header with logo, sign-in | Standard header | No | No | No |
| 3 | Multi-Column Footer | Medium | 5-section footer, social, language | Footer variant | No | No | No |
| 4 | Breadcrumb | Low | Hierarchical path navigation | Standard EDS | No | No | No |
| 5 | Left Sidebar Nav | Medium | Expandable sections, active states | Custom block | No | No | Low |

## 3.2 Hero & Banner

| # | Block | Complexity | Description | EDS Standard | Backend | Edge Worker | UI Ext |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 6 | Marketing Hero | Medium | Full-width headline + CTA + image | Hero variant | No | No | No |
| 7 | Consumer Hero | Medium | Headline + sign-in CTA, minimal | Hero variant | No | No | No |
| 8 | Video Hero | Medium | Hero with embedded video player | Hero variant | No | No | Low |
| 9 | Feature Announcement | Low | Highlighted news/feature banner | Standard banner | No | No | No |

## 3.3 Card Components

| # | Block | Complexity | Description | EDS Standard | Backend | Edge Worker | UI Ext |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 10 | Action Card (4-col) | Medium | Icon + title + desc + CTA grid | Cards variant | No | No | No |
| 11 | Feature Card (3-col) | Low | Icon + heading + text pillars | Columns variant | No | No | No |
| 12 | Course Card | Low | Title + duration + Launch CTA | Cards variant | No | No | No |
| 13 | Skill Type Card | Medium | 9 category cards with learn-more | Cards variant | No | No | No |
| 14 | Case Study Card | Medium | Video + partner + description | Cards variant | No | No | Low |
| 15 | Partner Logo Grid | Low | 12+ brand logos in grid | Logo grid | No | No | No |
| 16 | Profile Card | Low | Name + location + link | Cards variant | Possible | No | No |
| 17 | Blog Category Card | Low | Icon + title + desc + CTA | Cards variant | No | No | No |
| 18 | News/Press Card | Low | Headline + source + link | Cards variant | No | No | No |
| 19 | Vertical Industry Card | Medium | Image + vertical + desc + CTA | Cards variant | No | No | No |
| 20 | Resource Card | Low | Icon/image + title + link | Cards variant | No | No | No |

## 3.4 Content & Educational

| # | Block | Complexity | Description | EDS Standard | Backend | Edge Worker | UI Ext |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 21 | Value Proposition | Low | Heading + paragraph + CTA, alternating | Columns | No | No | No |
| 22 | Statistics/Social Proof | Low | Large numbers + context text | Custom | No | No | No |
| 23 | Executive Quote | Low | Photo + quote + attribution | Quote block | No | No | No |
| 24 | Step-by-Step Process | Low | Numbered progressive steps | Steps variant | No | No | No |
| 25 | Feature/Comparison Table | Medium | Multi-column with categories | Table block | No | No | No |
| 26 | Mission Pillars | Low | 4-column icon + title + text | Columns variant | No | No | No |
| 27 | SDK Integration Block | Medium | SDK name + desc + technical CTA | Custom | No | No | No |

## 3.5 Interactive Components

| # | Block | Complexity | Description | EDS Standard | Backend | Edge Worker | UI Ext |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 28 | Video Carousel | High | 4-slot rotating video with player | Custom block | No | No | Medium |
| 29 | Customer Success Carousel | Medium | Rotating case study cards | Carousel block | Possible | No | Low |
| 30 | Newsletter Signup | Low | Email + subscribe CTA | Form block | Yes-Qualtrics | No | No |
| 31 | Language Selector | Low | 9+ language dropdown | Custom nav | No | No | No |
| 32 | Search | High | Full-text developer portal search | Custom block | Yes-search API | Yes | Medium |
| 33 | Geographic Tabs | Medium | Tab switching for regions | Tabs block | No | No | Low |
| 34 | Sign-In Button | Medium | Amazon SSO redirect + tracking | Custom CTA | Yes-Amazon auth | No | No |
| 35 | Social Media Links | Low | Platform icons + links | Standard embed | No | No | No |
| 36 | Callout/Alert Box | Low | Dismissible notification banner | Banner block | No | No | No |
| 37 | PDF/Resource Download | Low | Document link with type indicator | Standard link | No | No | No |
| 38 | Line Break/Divider | Low | Visual section separator | Default content | No | No | No |

# 4. Page Counts by Template

| Template | Pages (Est.) | Auto-Migratable | Manual Migration | Reasoning |
| --- | --- | --- | --- | --- |
| Consumer Landing | 5-8 | 3-5 | 2-3 | Video carousel + auth needs custom work |
| Developer Portal Hub | 3-5 | 2-3 | 1-2 | Complex nav, search integration |
| Product/SKU Marketing | 15-20 | 12-15 | 3-5 | Mostly static, some video cases |
| Technical Product Detail | 10-12 | 8-10 | 2-3 | Diagrams, changelogs vary |
| Vertical Marketing | 8-10 | 6-8 | 2-3 | Carousels may be dynamic |
| Program/Community | 12-15 | 10-12 | 2-3 | Portfolio grids possibly DB-driven |
| Getting Started/Tutorial | 5-8 | 3-5 | 2-3 | Video embeds, LMS links |
| Training Catalog | 5-8 | 4-6 | 1-2 | Courses may be CMS-fed |
| People/Champions | 3-5 | 0 | 3-5 | Profile data from database |
| Blog Hub | 8-10 | 5-7 | 3-4 | Dynamic listings, categories |
| Brand Guidelines | 6-8 | 5-7 | 1-2 | Static with sidebar nav |
| Solution Provider Directory | 8-10 | 5-7 | 3-4 | Listings possibly dynamic |
| Feature Updates/Changelog | 3-5 | 2-3 | 1-2 | Table data may be API-fed |
| AI/SDK Showcase | 5-8 | 3-5 | 2-3 | Video cases, testimonials |
| Standards/Initiative | 3-5 | 2-3 | 1-2 | GitHub integration, video |
| TOTALS | ~108-144 | ~70-90 (62%) | ~38-54 (38%) |  |

# 5. Integrations Analysis

| # | Integration | Type | Complexity | Client/Server | Active/Legacy |
| --- | --- | --- | --- | --- | --- |
| 1 | Amazon CloudFront CDN | Infrastructure | Medium | Server-side | Active |
| 2 | Amazon SSO/OpenID | Authentication | High | Both | Active |
| 3 | Qualtrics | Embed/Plugin | Low | Client-side | Active |
| 4 | Developer Console (ASK) | API/Redirect | High | Server-side | Active |
| 5 | GitHub | External Link | Low | Client-side | Active |
| 6 | YouTube | Embed | Low | Client-side | Active |
| 7 | Slack Community | External Link | Low | Client-side | Active |
| 8 | Stack Overflow | External Link | Low | Client-side | Active |
| 9 | Sana LMS | Redirect | Medium | Client-side | Active |
| 10 | Amazon Media Services | CDN/Asset | Low | Server-side | Active |
| 11 | fls-na.amazon.com | Analytics | Medium | Client-side | Active |
| 12 | CloudFront Search Index | API | Medium | Client-side | Active |
| 13 | Amazon Science | External Link | Low | Client-side | Active |
| 14 | Developer Forums | External Platform | Medium | Server-side | Active |
| 15 | Social Media APIs | External Links | Low | Client-side | Active |
| 16 | Amazon.com Store | eCommerce Link | Low | Client-side | Active |
| 17 | Alexa+ Subscription | eCommerce | High | Server-side | Active |
| 18 | Video Player (Proprietary) | Embed | Medium | Client-side | Active |

# 6. Forms Analysis

| Category | Count | Complexity | Backend Required |
| --- | --- | --- | --- |
| Newsletter Signup ('Voice Mail') | 5-8 | Simple | Yes - Qualtrics |
| Developer Account Registration | 1 | High | Yes - Amazon SSO |
| Pitch/Application Form | 2-3 | Medium | Yes - CRM |
| Feedback Survey | 2-3 | Simple | Yes - Qualtrics |
| Contact Us | 1 | Medium | Yes - Ticketing |
| Training Enrollment (external) | 5-8 | N/A | External LMS |
| TOTAL | ~16-24 |  |  |

## 6.1 Complexity Breakdown

| Complexity | Count | Rationale |
| --- | --- | --- |
| Simple (1-2 fields) | 10-14 | Newsletter, feedback surveys |
| Medium (multi-field) | 3-5 | Contact, pitch applications |
| Complex (multi-step, auth) | 2-3 | Developer registration, console access |
| External (not migratable) | 5-8 | LMS enrollment, forums |

# 7. Offers & Personalization Analysis

No Adobe Target or equivalent third-party personalization engine detected. Personalization handled by Amazon's internal systems.

| Category | Instances | Complexity | Backend Required |
| --- | --- | --- | --- |
| Authenticated state (sign-in/out) | All pages | Medium | Yes - Session |
| Locale-based content | All pages | Medium | No - URL routing |
| New feature callout banners | 3-5 | Low | No - static |
| Context-aware device sync (consumer) | 2-3 | High | Yes - Amazon ecosystem |
| Alexa+ subscription upsell | 2-3 | Medium | Yes - subscription API |

# 8. Complex Use Cases & Observations

| # | Use Case | Instances | Location | Why Complex |
| --- | --- | --- | --- | --- |
| 1 | Developer Console SSO | All dev pages | Sign-in CTAs | Amazon SSO federation; cannot replicate in EDS |
| 2 | Multi-language (9+ locales) | All pages | Language selector | Full i18n framework with translated nav |
| 3 | Developer Portal Search | All dev pages | Header search | CloudFront-indexed; needs edge worker or search service |
| 4 | Video Carousel + Player | 2-3 pages | Consumer pages | Proprietary player, lazy loading, state mgmt |
| 5 | Champions Database | 1 + profiles | Champions page | DB-driven profiles, geographic filtering |
| 6 | Blog/Content Feed | 4+ sections | Blog hub | CMS-driven listings, categories, pagination |
| 7 | External LMS Integration | 5-8 pages | Training section | Course data from Sana, progress external |
| 8 | Partner/Provider Directory | 3-5 pages | Solution providers | Potentially DB-driven listings |
| 9 | Amazon Store Cross-Links | 5-8 pages | Shop Echo links | Deep linking with referral tracking |
| 10 | Subscription/Purchase Flow | 1-2 pages | Alexa+ upsell | Amazon subscription infrastructure |

# 9. Outlier Scenarios

| # | Scenario | Implementation | Complexity | EDS Approach | Effort (days) |
| --- | --- | --- | --- | --- | --- |
| 1 | Developer Console SSO | Amazon OpenID Connect, session cookies | Very High | Federated auth via edge worker | 15-20 |
| 2 | CloudFront Search | Pre-built index on CloudFront CDN | High | Algolia/Coveo or AEM search | 10-15 |
| 3 | Video Player Integration | Custom player, m.media-amazon.com | Medium | YouTube embeds or HTML5 video block | 5-8 |
| 4 | Champions Profile System | Backend DB, geographic tabs, profiles | Medium | Spreadsheet-driven or edge worker + DB | 8-12 |
| 5 | Blog CMS Integration | Separate CMS feeding blog content | High | AEM doc-based authoring or headless CMS | 12-18 |
| 6 | Training/LMS Redirect | External Sana platform | Low | Simple link cards; LMS stays external | 2-3 |
| 7 | Locale-Based Routing | 9+ languages, translated nav/content | High | AEM multi-language; edge worker locale | 15-20 |
|  | TOTAL |  |  |  | 67-96 |

# 10. Migration Estimates

## 10.1 Effort Breakdown

| Work Stream | Items | Effort (Days) | Notes |
| --- | --- | --- | --- |
| Design System Creation | 38 components | 25 | Tokens, typography, color, grid |
| Template Development | 15 templates | 30 | EDS page templates + block definitions |
| Standard Block Development | 25 blocks | 20 | Cards, heroes, columns, footers, nav |
| Complex Block Development | 8 blocks | 25 | Video carousel, search, nav, carousels |
| Integration Layer | 18 integrations | 35 | Auth, search, video, LMS, analytics, i18n |
| Content Migration - Automated | 70-90 pages | 10 | Scripted import for static pages |
| Content Migration - Manual | 38-54 pages | 25 | Dynamic pages, profiles, blog |
| Localization Framework | 9 languages | 15 | i18n structure, translated nav, locale routing |
| QA & Testing | All | 20 | Cross-browser, a11y, responsive, integration |
| Performance Optimization | All | 5 | Lighthouse 100, CWV, images |
| UAT & Stakeholder Review | All | 8 | Business validation |
| Documentation | - | 5 | Author guides |
| TOTAL |  | 273 |  |

## 10.2 Phase Summary

| Phase | Person-Days | Duration (Weeks) | Team Size |
| --- | --- | --- | --- |
| Phase 1: Design & Architecture | 55 | 4 | 3 |
| Phase 2: Core Development | 75 | 5 | 3 |
| Phase 3: Integration & Complex Features | 60 | 4 | 3 |
| Phase 4: Content Migration & i18n | 50 | 4 | 3 |
| Phase 5: QA, UAT & Launch | 33 | 3 | 2 |
| TOTAL | 273 person-days | ~20 weeks | 3 avg |

## 10.3 Cost Estimate

| Resource | Rate/Day | Days | Cost |
| --- | --- | --- | --- |
| Solution Architect | $1,800 | 25 | $45,000 |
| Senior Frontend Developer (x2) | $1,500 | 130 | $195,000 |
| Integration Developer | $1,600 | 50 | $80,000 |
| UX/Design Lead | $1,400 | 30 | $42,000 |
| Content Migration Specialist | $1,000 | 35 | $35,000 |
| QA Engineer | $1,200 | 25 | $30,000 |
| Project Management | $1,400 | 20 wks | $28,000 |
| TOTAL |  |  | ~$455,000 |

## 10.4 Risk Factors

| Risk | Impact | Probability | Mitigation |
| --- | --- | --- | --- |
| Amazon SSO integration complexity | +3 weeks | High | Early auth architecture spike |
| Search implementation challenges | +2 weeks | Medium | Evaluate Algolia/Coveo early |
| Video player replacement quality | +1 week | Low | Use standard HTML5/YouTube |
| Blog content volume exceeds estimate | +2 weeks | Medium | Prioritize recent content only |
| Localization scope growth | +3 weeks | High | Phase languages incrementally |
| Amazon internal stakeholder alignment | +2 weeks | High | Early governance agreement |

# 11. Recommendations

Migration Strategy:

• Exclude Amazon.com commerce pages - embedded in Amazon retail platform

• Developer Portal first - most content, best suited to EDS

• Consumer landing as showcase - high design quality proof-of-concept

• Auth via redirect - don't replicate SSO; redirect and handle tokens

• Search via third-party - Algolia/Coveo instead of CloudFront index

• Blog as doc-based - AEM document authoring for blog content

• Localization phased - Start English, add JP/DE/FR based on traffic

Out-of-Scope Items:

• Amazon.com product/commerce pages (deep retail integration)

• Developer Console applications (ASK, AVS, ACK)

• Sana LMS training platform content (keep as redirect)

• Developer Forums (separate platform)

• Amazon Science blog (separate domain/CMS)

Quick Wins (Weeks 1-4):

• Establish design tokens from existing patterns

• Migrate 15-20 static marketing pages (Programs, Branding)

• Set up EDS infrastructure with CI/CD

• Build global nav component and footer

# Appendix A: Asset Inventory

| Asset Type | Estimated Count | Source |
| --- | --- | --- |
| Hero/banner images | ~25-30 | CloudFront CDN |
| Product/SDK icons | ~40-50 | CloudFront CDN |
| Partner/brand logos | ~30-40 | Logo grids |
| Champion profile photos | ~50-80 | Champions section |
| Video content | ~15-20 | Embedded players |
| PDF/documentation files | ~10-15 | Brand guidelines |
| Total Digital Assets | ~170-235 |  |