Thermo Fisher Scientific

US Locale (thermofisher.com/us/en/)

AEM-to-EDS Migration Assessment

Version 1.0 | March 15, 2026

CONFIDENTIAL

# Executive Summary

This document provides a comprehensive migration assessment for thermofisher.com US locale (/us/en/) from Adobe Experience Manager (AMS) to Adobe Edge Delivery Services (EDS). The assessment covers technology stack analysis, page inventory, component catalog, integrations analysis, and a phased migration plan with effort estimates.

| Metric | Value |
| --- | --- |
| CMS Content Pages (US Locale) | 12,161 |
| Supplementary Pages (Product Catalog, Antibodies, etc.) | ~911,826 (out of EDS scope) |
| Unique Page Templates | 16 |
| Reusable Blocks/Components | 48 |
| Third-Party Integrations | 23 |
| Web Forms Identified | 12 |
| Design Variations (Same Content Model) | 15 |
| Locales Served | 35 (23 countries, 9 languages) |
| Estimated Migration Duration | 7-9 months (realistic) |
| Estimated Team Size | 8-12 people |

# 1. Current Technology Stack

The site is built on Adobe Experience Manager (AMS) with a server-rendered HTML architecture, supplemented by multiple client-side systems for commerce, personalization, and analytics.

| Layer | Technology | Details |
| --- | --- | --- |
| CMS | Adobe Experience Manager (AMS) | Server-rendered pages, AEM client libraries (/etc/designs/komodo/) |
| Frontend Framework | Vanilla JS + jQuery Migrate 3.4.1 | No SPA framework; progressive enhancement; BEM CSS |
| Commerce (Out of Scope) | Custom Java/AEM + React SPA | /order/, /store/ paths; React/Redux for product catalog |
| Blog (Out of Scope) | WordPress | acceleratingscience.com; API-fed into homepage |
| Search | Lucidworks Fusion | Migrated from Oracle Endeca; typeahead autocomplete |
| Analytics | Adobe Analytics + AEP/Alloy v2.23 | digitalData layer; edge.adobedc.net data collection |
| Tag Management | Adobe Launch (Experience Platform Tags) | assets.adobedtm.com; multiple extension bundles |
| Personalization | Adobe Target + DM Dynamic Offers | Pre-hiding containers; server-side offer injection |
| Authentication | Custom SSO + Gigya/SAP CDC | identity.thermofisher.com; /auth/initiate flow |
| CDN / Security | Akamai | Bot management, edge caching, WAF |
| Cookie Consent | TrustArc | GDPR compliance; consent.truste.com |
| Chat | Custom + Magellan GenAI (feature-flagged) | chat-api.thermofisher.com; Vue.js-based |
| Accessibility | UserWay | Widget overlay; account P3pDlQucOz |
| Feedback | Medallia / Kampyle | Form ID 29308; floating button |
| Design System | HelveticaNeue, 11 weights, WOFF2 | 7 breakpoints; #e71316 brand red |

# 2. Integrations Analysis

23 third-party integrations identified across the site. Each integration is classified by type and complexity for migration planning.

| # | Integration | Type | Complexity | Reference / Evidence |
| --- | --- | --- | --- | --- |
| 1 | Adobe Analytics | Embed / API | Medium | _satellite object, digitalData layer on all pages |
| 2 | Adobe Experience Platform (Alloy) | API / SDK | High | alloy.min.js v2.23.0, edge.adobedc.net |
| 3 | Adobe Launch (EP Tags) | Embed | High | assets.adobedtm.com, multiple RC bundles |
| 4 | Adobe Target | API | High | /api/store/recommendations/recommendation/target/attributes |
| 5 | DM Dynamic Offers | Custom Code | High | /dm-offers/offers.min.js; CSS template injection |
| 6 | OOB Recommendation Engine | API | Medium | /api/store/recommendations/oobRecommendation/ |
| 7 | Price & Availability API | API | High | /api/store/recommendations/priceandavail (POST, 24 items/batch) |
| 8 | TF Identity Service | Custom Code | High | identity.thermofisher.com; /auth/initiate SSO |
| 9 | Gigya / SAP CDC | Plugin | Medium | digitalData.user.gigyaId field |
| 10 | Lucidworks Fusion | Embed / API | High | /search/searchbar/, /search/static/resources/js/signals.min.js |
| 11 | Custom Chat System | Embed / API | High | chat-api.thermofisher.com; eligibility API; Vue.js app |
| 12 | Magellan GenAI Chat | API (Feature-flagged) | High | Cookie ts_magellan_genai; A/B tested |
| 13 | TrustArc | Embed | Medium | consent.truste.com/notice; Accept/Reject/Manage |
| 14 | Akamai CDN + Bot Mgmt | Infrastructure | High | akacd_TFCOM_Prod_AWS_Publish; bot detection scripts |
| 15 | UserWay Accessibility | Embed | Medium | cdn.userway.org/widgetapp/; API tunings |
| 16 | Medallia / Kampyle | Embed | Medium | nebula-cdn.kampyle.com; form IDs 29308, 46937 |
| 17 | WordPress Blog API | API | Medium | admin.acceleratingscience.com/wp-json/as-api/v1/blog-feed |
| 18 | MasterControl | External Link | Low | thermofisher.mastercontrol.com (privacy policy) |
| 19 | Adobe Cart System | API | High | /api/store/carts/{cartId}/minicart; cartV3Enabled |
| 20 | jQuery Migrate 3.4.1 | Embed | Low | Legacy compatibility; deprecated APIs in use |
| 21 | Hotjar | Embed | Low | Cookie _hjSessionUser_4539 (corporate subdomain) |
| 22 | Form Security (CSRF) | Custom Code | Low | Cookie formSecurity |
| 23 | TrustArc GTM Bridge | Plugin | Low | gtm=true parameter in consent notice |

# 3. Pages and Assets Inventory

## 3.1 CMS Content Pages (In EDS Scope)

The US locale sitemap (sitemap-us-en.xml) contains 12,161 CMS-authored pages. These are the pages targeted for EDS migration.

| Section | Page Count | % of Total | Avg Depth |
| --- | --- | --- | --- |
| Life Science | 3,476 | 28.6% | 4-5 |
| Industrial | 1,978 | 16.3% | 4-5 |
| References / Protocols | 1,545 | 12.7% | 3-4 |
| Technical Resources | 1,223 | 10.1% | 3-4 |
| Products & Services (incl. Promotions) | 837 | 6.9% | 3-4 |
| Clinical | 628 | 5.2% | 4-5 |
| About Us / Events | 573 | 4.7% | 2-3 |
| Electron Microscopy | 418 | 3.4% | 3-4 |
| Materials Science | 282 | 2.3% | 3-4 |
| Brands | 250 | 2.1% | 2-3 |
| Bioprocessing | 215 | 1.8% | 3-4 |
| Chemicals | 169 | 1.4% | 3-4 |
| Virtual / 3D Tours | 109 | 0.9% | 2 |
| Other (Events, New Ideas, Global, etc.) | 458 | 3.8% | 2-3 |
| TOTAL | 12,161 | 100% | — |

## 3.2 Supplementary Pages (Out of EDS Scope)

These application-generated pages are served by dedicated systems (React SPA, antibody app, etc.) and are NOT in scope for EDS CMS migration.

| System | URL Pattern | Approx. Pages | Technology |
| --- | --- | --- | --- |
| Product Catalog | /order/catalog/product/{SKU} | 393,254 | React SPA |
| Antibodies | /antibody/product/{name}/{id} | 359,830 | Dedicated App |
| Citations | /order/catalog/product/{SKU}/citations | 109,062 | React SPA |
| FAQ Pages | /store/sitemap/faq/ | 32,122 | React SPA |
| Antibody Videos | Video sitemap | 11,336 | Video CDN |
| CAS Chemical Search | /search/cas/{CAS-number} | 5,648 | Search App |
| Other (OneLambda, Allergy, etc.) | Various | 574 | Dedicated Apps |
| TOTAL OUT OF SCOPE | — | ~911,826 | — |

## 3.3 Assets

Images and media assets are served from AEM DAM (/content/dam/) and Adobe Dynamic Media. Key observations:

- Hero banners and promotional images: dynamically served via DM Offers system

- Product images: served from product catalog CDN (shared across locales)

- Brand logos and icons: served from /etc/designs/ client libraries

- Blog images: served from WordPress (acceleratingscience.com)

- Estimated unique image assets: 15,000-25,000 (excluding product catalog)

# 4. Page Grouping by Traffic

Pages are classified into HIGH, MEDIUM, and LOW traffic groups based on URL depth, section importance, and typical user navigation patterns for a B2B scientific commerce site.

| Traffic Group | Page Count | % of Total | Description | Migration Priority |
| --- | --- | --- | --- | --- |
| HIGH | 233 | 1.9% | Homepage, L1 section hubs (27), L2 major categories (205) | Phase 1 - First |
| MEDIUM | 4,116 | 33.8% | L3-L4 subcategories, brand pages, promotions (710), events (562), virtual tours | Phase 2 |
| LOW | 7,812 | 64.2% | Depth 5+ pages, reference articles (1,545), technical library (1,200+), deep subpages | Phase 3 |

### Traffic Group Breakdown by Section

| Section | HIGH | MEDIUM | LOW |
| --- | --- | --- | --- |
| Life Science | 24 | 1,168 | 2,284 |
| Industrial | 18 | 569 | 1,391 |
| References | — | 8 | 1,537 |
| Technical Resources | — | 14 | 1,209 |
| Products & Services | 1 | 126 | 710 |
| Clinical | 12 | 76 | 540 |
| About Us / Events | 1 | 91 | 481 |
| Electron Microscopy | 1 | 110 | 307 |
| Brands | 18 | 86 | 146 |
| Support | 1 | 12 | — |
| Other | 157 | 1,856 | 1,207 |
| TOTAL | 233 | 4,116 | 7,812 |

# 5. Templates Inventory

16 unique page templates identified across the US locale. Templates are classified by complexity and migration approach.

| # | Template | Complexity | Count | Reasoning | Example URL |
| --- | --- | --- | --- | --- | --- |
| 1 | Homepage | High | 1 | Dynamic offers, personalization, carousels, product carousel with pricing, blog feed | thermofisher.com/us/en/home.html |
| 2 | L1 Category Hub | Medium | 27 | H1 title, featured links, 4-column category grid, banner images | /us/en/home/life-science.html |
| 3 | L2 Category | High | 205 | Hero with CTA, image cards, value props, application links, research areas | /us/en/home/life-science/antibodies.html |
| 4 | L3-L5 Product Category | Medium | 8,300 | Nested categories with sidebar nav, product specs, comparison content | /us/en/home/life-science/pcr/real-time-pcr.html |
| 5 | Brand Page | Medium | 250 | Brand logo, sidebar nav, multi-section content, resource cards | /us/en/home/brands/thermo-scientific.html |
| 6 | Technical Resources | Medium | 1,223 | Reference library pages, learning centers, document hubs | /us/en/home/technical-resources.html |
| 7 | References / Protocols | Low | 1,545 | Structured document pages, text-heavy, minimal interactivity | /us/en/home/references/protocols.html |
| 8 | Support Hub | Medium | 13 | Multi-column link grid, collapsible TOC, contact sidebar | /us/en/home/support.html |
| 9 | Promotions / Campaign | Medium | 710 | Promo hero, product cards, CTAs, time-sensitive content | /us/en/home/products-and-services/promotions.html |
| 10 | About Us | Low | 91 | Corporate content, text-focused, external links | /us/en/home/about-us.html |
| 11 | Events / Webinars | Medium | 562 | Table-based layout, client-side filter, date-driven content | /us/en/home/events.html |
| 12 | Virtual / 3D Tours | High | 109 | Embedded 3D product viewers, interactive experiences | /us/en/home/virtual/vanquish-horizon-hplc.html |
| 13 | Clinical | Medium | 628 | Category pattern with clinical-specific content | /us/en/home/clinical/diagnostic-testing.html |
| 14 | Industrial | Medium | 1,978 | Category pattern with industrial-specific content | /us/en/home/industrial/chromatography.html |
| 15 | Global / Legal | Low | 52 | Simple text pages (terms, privacy, policies) | /us/en/home/global/terms-and-conditions.html |
| 16 | Misc / Legacy | Low | 128 | Campaign landing pages, test pages, unsubscribe | /us/en/home/homepage2020.html |

Figure 1: Homepage Template — Hero carousel, product offers, promotions, blog feed

Figure 2: L1 Category Template — Life Sciences hub with 4-column category grid

Figure 3: L2 Category Template — Antibodies with hero, image cards, research areas

Figure 4: Brand Page Template — Thermo Scientific with sidebar nav, resource cards

Figure 5: Support Hub Template — Multi-column link grid with collapsible TOC

Figure 6: Documents & Certificates — CoA, SDS, Manuals lookup forms

Figure 7: Promotions Template — Card grid with promo imagery and CTAs

Figure 8: Events Template — Table-based layout with client-side filter

# 6. Blocks / Components Catalog

48 unique reusable blocks/components identified. Where the same content model has different visual layouts, these are cataloged as design variations rather than separate blocks.

## 6.1 Navigation Components (10)

| Block | Complexity | Behavior & Functionality | Pages | Reference URL |
| --- | --- | --- | --- | --- |
| Global Header Bar | High | Fixed position, responsive (60px mobile/88px desktop), logo, search, utility icons, z-index:80 | All pages | /us/en/home.html |
| Promotional Top Bar | Medium | Rotating promo banner above header, full-width clickable link, dismiss button | All pages | /us/en/home.html |
| Mega Navigation Menu | High | Left slide-out on mobile (380px), horizontal mega-menu desktop (993px+), multi-level hierarchy | All pages | /us/en/home.html |
| Breadcrumb Trail | Low | Home > Category > Subcategory with ">" separator, linked parents | Category, Brand | /us/en/home/life-science.html |
| Utility Bar | Medium | Order Status, Quick Order, Sign In, Bell, Cart icons; hidden below 993px | All pages | /us/en/home.html |
| Account Dropdown | Medium | 330px dropdown with user name, My Account, loyalty info, Sign Out | All pages (auth) | /us/en/home.html |
| Left Sidebar Nav | Medium | Sticky vertical nav: Popular Products, Key Applications, Resources sections | Brand pages | /us/en/home/brands/thermo-scientific.html |
| Collapsible TOC | Medium | Accordion button expanding/collapsing page content outline | Support | /us/en/home/support.html |
| In-Page Anchor Nav | Low | Horizontal link list linking to #anchor sections within page | Brand pages | /us/en/home/brands/thermo-scientific.html |
| Country/Locale Selector | Low | Footer element: flag icon + country name, locale picker modal | All pages | /us/en/home.html |

## 6.2 Hero & Banner Components (5)

| Block | Complexity | Behavior & Functionality | Pages | Reference URL |
| --- | --- | --- | --- | --- |
| Full-Width Hero Banner | High | DM Offers dynamic content, background image, overlaid text + CTA, multiple rotating variants | Homepage | /us/en/home.html |
| Category Hero Banner | Medium | Colored background (#A51C36), H1 heading, subtitle, primary CTA button | L2 categories | /us/en/home/life-science/antibodies.html |
| Brand Hero Image | Low | Large brand logo image with in-page anchor nav below | Brand pages | /us/en/home/brands/thermo-scientific.html |
| Page Title Header | Low | Plain H1 on light gray background strip | L1, Support | /us/en/home/life-science.html |
| Sticky Bottom Promo Bar | Medium | Fixed bottom bar with promo text, CTA link, dismiss "x" button | Homepage, L1, L2 | /us/en/home.html |

## 6.3 Content Blocks (11)

| Block | Complexity | Behavior & Functionality | Design Variations |
| --- | --- | --- | --- |
| Featured Education Section | Medium | H2 + "See all" link, teaser cards with full-width image, title, bullet points, CTA | — |
| Blog Post List | Medium | H2 + "View all" link, 3 entries: thumbnail, title, date, "Read more" | — |
| Category Description Grid | Medium | 4-column grid of H3-linked categories with paragraph descriptions (18 categories) | — |
| Value Proposition Cards | Medium | 3-card horizontal: image, H4, description, "Learn more" link | — |
| Application Links + Image | Medium | Left image + right 2-column link list with arrow icons | Variation: Research Areas (3-col no image) |
| Research Areas Grid | Low | 3-column grid of arrow-prefixed links (9 links) | Variation of Application Links |
| Related Categories | Medium | Image + 2-column link list with arrows | — |
| Brand Description Block | Low | H2 + multi-paragraph rich text with inline links, separated by <hr> | — |
| Multi-Column Support Grid | High | 2-column layout with 10+ H2/H3 categorized link sections | — |
| Supply Center Block | Low | H2 + subtitle + CTA link, text-only, no image | — |
| Regulatory Disclaimer | Low | Single-line "For Research Use Only" text at page bottom | — |

## 6.4 Card Components (10)

| Block | Complexity | Behavior & Functionality | Design Variations |
| --- | --- | --- | --- |
| Promotional Pod Cards (3-up) | Medium | Background image, short text, CTA link; part of DM offers system | — |
| Product Carousel Card | High | Catalog #, name, image, strikethrough price, special offer, savings %, "Add to cart" | — |
| Promotion Banner Card (2-up) | Medium | Background image, text overlay, badge label, primary CTA button | Variation: 4-up layout |
| New Product Card (3-up) | Medium | Product image, title, description, "Learn more" CTA | — |
| Educational Content Card | Low | 3-up horizontal: icon image + linked title, no description | — |
| Related Pages Card (2-up) | Low | Icon + linked title only | — |
| Resource Card w/ Thumbnail | Medium | 70x70 thumbnail left, H3 linked title + description right | — |
| Category Image Card (2x2) | Medium | Full-width image + linked label below; grid layout | — |
| Event Table Row | Medium | Table-based layout: date, title, location, type, CTA | — |
| Promotion Listing Card | Medium | Image, promo badge, description, CTA; filterable grid | Variation: with/without badge |

## 6.5 Interactive & Third-Party Components (12)

| Block | Complexity | Behavior & Functionality | Pages |
| --- | --- | --- | --- |
| Product Offer Carousel | High | 4 visible cards, arrow + dot nav, 24 products, pricing, "Add to cart" | Homepage |
| Promotional Carousel | Medium | 2-4 visible cards, arrow + dot navigation | Homepage |
| Global Search Bar | High | Typeahead autocomplete, provider dropdown, mobile full-screen overlay | All pages |
| Cookie Consent Banner | Medium | TrustArc: Accept All / Reject All / Manage Settings | All pages |
| Cart Drawer Sidebar | High | Right-slide 440px, product list, pricing, suggested products, checkout CTA | All pages |
| Notification Bell Dropdown | Medium | 420px dropdown, scrollable notifications, timestamps, "See All" | All pages |
| TrustArc Cookie Manager | High | Full GDPR consent system, tag injection management | All pages |
| Adobe Launch/DTM | High | Tag management, Adobe Target personalization with 3s pre-hiding | All pages |
| Kampyle/Medallia Feedback | Medium | Fixed "Feedback" button, form ID 29308 | Most pages |
| AI Chat Widget | High | Chat launcher, eligibility API, Vue.js app | Category, Support |
| Accessibility Quick Menu | Medium | 4 buttons: skip content, visual impairment, a11y menu, a11y nav | All pages |
| Global Footer (5-column) | High | Ordering, Support, Resources, About TF, Portfolio; legal bar | All pages |

# 7. Page Counts by Template (Migration Approach)

| Template | Total | Auto-Migratable | Manual Migration | Notes |
| --- | --- | --- | --- | --- |
| Homepage | 1 | 0 | 1 | Dynamic offers, personalization, carousels require manual setup |
| L1 Category Hub | 27 | 22 | 5 | Standard grid pattern; some have custom promo banners |
| L2 Category | 205 | 155 | 50 | Hero + cards + links; variable section counts |
| L3-L5 Product Category | 8,300 | 7,300 | 1,000 | Bulk-importable with templates; edge cases need manual review |
| Brand Page | 250 | 190 | 60 | Sidebar nav + mixed content; some heavily customized |
| Technical Resources | 1,223 | 1,050 | 173 | Reference content, mostly structured text |
| References / Protocols | 1,545 | 1,400 | 145 | Highly structured document pages |
| Support Hub | 13 | 0 | 13 | Complex multi-column layouts, all need manual work |
| Promotions / Campaign | 710 | 550 | 160 | Variable layouts, some time-sensitive logic |
| About Us | 91 | 75 | 16 | Text-focused, some link to corporate subdomain |
| Events / Webinars | 562 | 450 | 112 | Table-based with filter; date-driven content |
| Virtual / 3D Tours | 109 | 0 | 109 | Embedded 3D viewers need custom implementation |
| Clinical | 628 | 520 | 108 | Standard category pattern with clinical specifics |
| Industrial | 1,978 | 1,700 | 278 | Standard category pattern, deepest hierarchy |
| Global / Legal | 52 | 48 | 4 | Simple text pages |
| Misc / Legacy | 128 | 40 | 88 | Campaign pages, test pages, varied layouts |
| TOTALS | 12,161 | 9,500 (78%) | 2,661 (22%) | — |

# 8. Complex Use Cases & Observations

| # | Use Case | Instances | Where Found | Why Complex |
| --- | --- | --- | --- | --- |
| 1 | Product Recommendation Engine (Adobe Target) | 1 carousel + multiple placements | Homepage, category pages | Real-time API calls to /api/store/recommendations/; personalized per user context (region, cart, history). Requires EDS integration with Target APIs. |
| 2 | Dynamic Pricing Display | 24+ products per carousel | Homepage Online Offers | Dual pricing (regular + special offer), savings calculation, real-time price API. Currency/locale-aware. |
| 3 | DM Dynamic Offers System | 3-5 placements per page | Homepage, category pages | Server-side personalization injecting HTML into placeholders. 200+ country code validation. CSS template loading. Retry mechanism (25 attempts). |
| 4 | Geolocation / Locale Detection | Global | 35 locales, 23 countries | Cookie-based (CK_ISO_CODE), hreflang tags, marketing region mapping. EDS needs edge-side detection or cookie routing. |
| 5 | Real-Time Cart Management | Global | All pages (mini-cart) | Server-side cart with cartId cookie, version flag (cartV3Enabled), suggested products. Cross-page persistence. |
| 6 | Certificate of Analysis Lookup | 1 form | Documents & Certificates page | AJAX lot/serial number lookup against backend API. Critical for regulated customers. |
| 7 | Safety Data Sheet Search | 1 form | Documents & Certificates page | Catalog number-based document retrieval. Regulatory compliance requirement. |
| 8 | AI Chat (Magellan GenAI) | Feature-flagged | Category, Support pages | Generative AI-powered chat being A/B tested. Feature flag via cookie ts_magellan_genai. |
| 9 | Multi-Step Contact Routing | 1 hub | /store/v2/contact-us | 6 topic cards leading to specialized contact methods. Real-time chat eligibility API check. |
| 10 | Event Table with Client-Side Filter | 1 page + subpages | /us/en/home/events.html | Table-based layout with text search filtering. Not server-side search. |
| 11 | WordPress Blog Feed Integration | 1 section | Homepage | API-fed content from acceleratingscience.com. Dynamic date/title/thumbnail rendering. |
| 12 | Virtual / 3D Product Tours | 109 pages | /us/en/home/virtual/* | Embedded interactive 3D viewers. Each product has custom viewer configuration. |

# 9. Web Forms Analysis

12 form types identified across the site. Forms are grouped by structure similarity and tagged by complexity.

| # | Form | Location | Complexity | Fields | Reasoning |
| --- | --- | --- | --- | --- | --- |
| 1 | Global Search Bar | All pages (header) | High | 1 text + 1 dropdown | Typeahead autocomplete, Lucidworks integration, mobile-responsive overlay, search signals analytics |
| 2 | Contact Us Hub | /store/v2/contact-us | High | 6 topic cards + sub-forms | Multi-step routing, chat eligibility API, multiple contact methods per topic |
| 3 | CoA Lookup | Documents & Certificates | Medium | 1 text + 1 submit | AJAX lot/serial number lookup against backend API |
| 4 | SDS Lookup | Documents & Certificates | Medium | 1 text + 1 submit | AJAX catalog number lookup; regulatory compliance |
| 5 | Manuals & Guides Lookup | Documents & Certificates | Medium | 1 text + 1 submit | AJAX catalog number lookup |
| 6 | FAQ Search | Documents & Certificates | Medium | 1 text + 1 submit | AJAX catalog number lookup |
| 7 | Shopping Cart / Mini-Cart | All pages (sidebar) | High | Qty selectors + remove buttons | Cart API integration, real-time updates, suggested products |
| 8 | Authentication / Sign-In | Header account | High | SSO redirect flow | identity.thermofisher.com; Gigya/SAP CDC integration |
| 9 | Medallia Feedback | Floating button | Medium | Survey form | Kampyle SDK; form ID 29308 |
| 10 | Cookie Consent | Bottom banner | Low | Accept / Reject / Manage | TrustArc integration |
| 11 | Event Text Filter | Events page | Low | 1 text input | Client-side table filtering |
| 12 | Webinar Registration | /global/forms/* | Medium | 5-10 fields | Standardized registration form template for events/webinars |

### Form Complexity Summary

| Complexity | Count | Forms |
| --- | --- | --- |
| High | 4 | Global Search, Contact Hub, Shopping Cart, Authentication |
| Medium | 6 | CoA Lookup, SDS Lookup, Manuals Lookup, FAQ Search, Medallia Feedback, Webinar Registration |
| Low | 2 | Cookie Consent, Event Text Filter |

# 10. Analysis Summary

| Category | Total | Low | Medium | High |
| --- | --- | --- | --- | --- |
| Page Templates | 16 | 4 | 8 | 4 |
| Blocks / Components | 48 | 14 | 22 | 12 |
| Design Variations | 15 | 8 | 5 | 2 |
| Third-Party Integrations | 23 | 5 | 7 | 11 |
| Web Forms | 12 | 2 | 6 | 4 |
| Complex Use Cases | 12 | — | 4 | 8 |

Key Metrics:

- Total CMS pages in scope: 12,161

- Auto-migratable pages: 9,500 (78%)

- Manual migration pages: 2,661 (22%)

- High-traffic pages (migration priority): 233

- Out-of-scope application pages: ~911,826

- Supported locales: 35 (potential for multi-locale rollout)

# 11. Migration Estimates

## 11.1 Effort Summary

| Activity | Optimistic (days) | Realistic (days) | Pessimistic (days) |
| --- | --- | --- | --- |
| Discovery & Planning | 15 | 20 | 30 |
| Design System Migration | 15 | 20 | 25 |
| Core Block Development (48 components) | 80 | 110 | 140 |
| Integration Layer (23 integrations) | 45 | 65 | 85 |
| Import Infrastructure (parsers, transformers) | 30 | 45 | 60 |
| Content Migration (12,161 pages) | 90 | 130 | 175 |
| QA & Validation (visual, a11y, performance) | 45 | 65 | 85 |
| UAT & Launch (stakeholder review, cutover) | 20 | 30 | 40 |
| TOTAL | 340 | 485 | 640 |

## 11.2 Team & Timeline

| Scenario | Team Size | Duration | Total Person-Days | Cost @ $150-200/hr |
| --- | --- | --- | --- | --- |
| Optimistic | 6-8 | 5-6 months | 340 | $408K - $544K |
| Realistic | 8-12 | 7-9 months | 485 | $582K - $776K |
| Pessimistic | 10-14 | 9-12 months | 640 | $768K - $1.02M |

# 12. Three-Phase Migration Plan

The migration is structured into 3 sequential phases with no parallel execution. Each phase has defined workstreams, deliverables, and exit criteria.

## 12.1 Sequential Roadmap

PHASE 1: Foundation          PHASE 2: Build & Migrate       PHASE 3: Scale & Launch

Month 1 ---- Month 3         Month 4 ---- Month 7          Month 8 ---- Month 9

┌─────────────────────┐    ┌───────────────────────┐    ┌─────────────────────┐

│ AEM: Content Audit   │    │ AEM: Bulk Import       │    │ AEM: Remaining Pages │

│   Template Mapping   │    │   Manual Migration     │    │   Content Freeze     │

│   Asset Inventory    │    │   Content Validation   │    │   Final Validation   │

├─────────────────────┤    ├───────────────────────┤    ├─────────────────────┤

│ EDS: Design System   │    │ EDS: All 48 Blocks    │    │ EDS: Perf Tuning     │

│   Core Blocks (15)   │    │   Template Refinement  │    │   SEO Validation     │

│   Header/Footer      │    │   Visual QA            │    │   Lighthouse 100     │

├─────────────────────┤    ├───────────────────────┤    ├─────────────────────┤

│ INT: Analytics Setup  │    │ INT: Target/Offers     │    │ INT: E2E Testing     │

│   Search POC         │    │   Cart Integration     │    │   DNS Cutover        │

│   Auth Planning      │    │   Chat/Consent/A11y   │    │   Monitoring Setup   │

└─────────────────────┘    └───────────────────────┘    └─────────────────────┘

EXIT: 233 HIGH pages       EXIT: 4,116 MED pages        EXIT: All 12,161 pages

## 12.2 Phase 1: Foundation (Months 1-3)

Establish the EDS project, migrate design system, build core blocks, and migrate all HIGH-traffic pages (233 pages).

### AEM Workstream

| Activity | Duration | Deliverables |
| --- | --- | --- |
| Content Audit & Template Mapping | 2 weeks | Complete page-template mapping for all 12,161 pages |
| Asset Inventory | 1 week | Catalog of 15-25K unique images with source/format/dimensions |
| Content Export Tooling | 2 weeks | AEM content extraction scripts and bulk export pipeline |
| HIGH Page Content Prep | 3 weeks | Content for 233 high-traffic pages exported, cleaned, validated |

### EDS Workstream

| Activity | Duration | Deliverables |
| --- | --- | --- |
| EDS Project Setup | 1 week | GitHub repo, aem.live config, local dev environment |
| Design System Migration | 3 weeks | CSS custom properties, HelveticaNeue fonts, 7 breakpoints, brand colors |
| Global Header Block | 2 weeks | Responsive header with search, utility bar, mega nav |
| Global Footer Block | 1 week | 5-column footer with legal bar and locale selector |
| Core Blocks (15 priority) | 4 weeks | Hero, cards, content blocks, breadcrumbs, sidebar nav |
| HIGH Pages Import & Validation | 2 weeks | 233 pages migrated, visually verified against original |

### Integrations Workstream

| Activity | Duration | Deliverables |
| --- | --- | --- |
| Analytics Setup (Adobe Analytics + AEP) | 2 weeks | digitalData layer, Launch integration, event tracking |
| Search POC (Lucidworks) | 2 weeks | Searchbar integration proof-of-concept on EDS |
| Auth Architecture Planning | 1 week | SSO flow design for identity.thermofisher.com on EDS |
| Cookie Consent (TrustArc) | 1 week | TrustArc script integration and consent flow |

Phase 1 Exit Criteria:

- 233 HIGH-traffic pages live on EDS preview environment

- Design system fully implemented with visual parity

- 15 core blocks functional and responsive

- Analytics and consent tracking operational

## 12.3 Phase 2: Build & Migrate (Months 4-7)

Complete all block development, migrate MEDIUM-traffic pages (4,116 pages), and implement all integrations.

### AEM Workstream

| Activity | Duration | Deliverables |
| --- | --- | --- |
| Bulk Import Pipeline Execution | 4 weeks | ~3,200 auto-migratable MEDIUM pages imported |
| Manual Migration (Complex Pages) | 4 weeks | ~916 MEDIUM pages requiring manual content work |
| Content Validation & QA | 3 weeks | Visual regression testing against original for all MEDIUM pages |
| Asset Migration | 2 weeks | All images and media for MEDIUM pages transferred |
| Redirect Mapping | 1 week | URL mapping document for all migrated pages |

### EDS Workstream

| Activity | Duration | Deliverables |
| --- | --- | --- |
| Remaining Blocks (33) | 6 weeks | All 48 blocks complete: interactive, commerce, third-party widgets |
| Product Carousel Block | 2 weeks | Carousel with pricing, add-to-cart, Target API integration |
| Template Refinement | 2 weeks | All 16 templates polished for content author experience |
| Visual QA & Responsive Testing | 3 weeks | Cross-browser, cross-device validation for all blocks |
| Accessibility Audit | 1 week | WCAG 2.1 AA compliance for all blocks and pages |

### Integrations Workstream

| Activity | Duration | Deliverables |
| --- | --- | --- |
| Adobe Target / DM Offers | 3 weeks | Personalization engine on EDS with pre-hiding, offer injection |
| Cart Integration | 2 weeks | Cart drawer sidebar, add-to-cart, mini-cart API on EDS pages |
| Lucidworks Search (Full) | 2 weeks | Complete searchbar with typeahead, signals, provider selector |
| Chat Widget (Custom + Magellan) | 2 weeks | Chat launcher, eligibility API, GenAI feature flag |
| UserWay Accessibility | 1 week | Accessibility overlay widget integration |
| Medallia Feedback | 1 week | Kampyle SDK integration, floating feedback button |
| WordPress Blog Feed | 1 week | API integration for homepage blog section |

Phase 2 Exit Criteria:

- 4,349 pages (HIGH + MEDIUM) live on EDS preview

- All 48 blocks complete and tested

- All 23 integrations functional

- Visual regression pass rate > 95%

## 12.4 Phase 3: Scale & Launch (Months 8-9)

Migrate all remaining LOW-traffic pages (7,812 pages), performance tuning, SEO validation, and production launch.

### AEM Workstream

| Activity | Duration | Deliverables |
| --- | --- | --- |
| Bulk Import: Remaining LOW Pages | 3 weeks | ~6,300 auto-migratable LOW pages imported |
| Manual Migration: Complex LOW Pages | 2 weeks | ~1,512 LOW pages requiring manual work |
| Content Freeze & Final Validation | 1 week | No new AEM content changes; final content verification |
| Redirect Implementation | 1 week | All 12,161 redirects configured and tested |

### EDS Workstream

| Activity | Duration | Deliverables |
| --- | --- | --- |
| Performance Optimization | 2 weeks | LCP < 2.5s, CLS < 0.1, FID < 100ms on all templates |
| SEO Validation | 1 week | Meta tags, structured data, sitemap, canonical URLs verified |
| Lighthouse Score Target: 100 | 1 week | PageSpeed Insights validation on all template types |
| Edge Worker Configuration | 1 week | Akamai/EDS edge rules for locale routing, caching, redirects |

### Integrations Workstream

| Activity | Duration | Deliverables |
| --- | --- | --- |
| End-to-End Integration Testing | 2 weeks | Full test suite: analytics, search, cart, auth, chat, consent |
| DNS Cutover Planning & Execution | 1 week | Phased DNS migration with rollback plan |
| Production Monitoring Setup | 1 week | Error tracking, performance monitoring, uptime alerts |
| Hypercare / Post-Launch Support | 2 weeks | Dedicated team for issue triage and hotfixes |

Phase 3 Exit Criteria:

- All 12,161 pages live on EDS production

- Lighthouse score >= 95 on all template types

- All redirects functional with zero 404 errors

- All integrations verified in production

- Hypercare team in place for 2-week post-launch

# 13. Assumptions & Boundary Conditions

## 13.1 Assumptions

- AEM AMS environment remains available for content extraction throughout the migration period

- Product catalog pages (/order/catalog/, /antibody/, /search/) remain on their current React SPA and are NOT migrated to EDS

- WordPress blog (acceleratingscience.com) remains on WordPress; only the API feed integration is migrated

- corporate.thermofisher.com (About Us) remains a separate AEM instance and is NOT in scope

- Identity service (identity.thermofisher.com) remains as-is; EDS integrates via redirect-based SSO

- Content authors will use AEM Universal Editor or Google Docs/Sheets for EDS content authoring

- Existing Akamai CDN configuration can be adapted for EDS edge delivery

- No new feature development during migration (feature freeze on CMS pages)

- Image assets can be referenced via existing CDN URLs (no re-hosting required initially)

## 13.2 Boundary Conditions (Scope Creep Risks)

| Risk | Impact | Likelihood | Mitigation |
| --- | --- | --- | --- |
| Multi-locale rollout requested | High — 34 additional locales × 12K pages each | Medium | Scope US-only first; design for locale reuse from Day 1 |
| Product catalog pages added to scope | Very High — 393K+ React SPA pages | Low | Maintain clear boundary: /order/* stays on React SPA |
| Custom eCommerce on EDS | High — cart/checkout rebuild | Low | Keep cart as shared JS widget; don't rebuild commerce |
| New brand/design refresh during migration | High — rework all blocks and CSS | Medium | Freeze design system in Phase 1; absorb changes post-launch |
| Legacy page discovery (unlisted pages) | Medium — additional manual migration | High | Buffer 15% in estimates for undiscovered content |
| Third-party integration changes | Medium — API contract changes | Medium | Lock integration versions; defer upgrades to post-launch |
| Performance targets increased | Medium — additional optimization | Low | Design for 100 Lighthouse from start; use EDS best practices |
| Accessibility compliance upgrade (WCAG 2.2) | Medium — additional testing/remediation | Medium | Build to WCAG 2.1 AA; assess 2.2 delta post-launch |
| Content authoring training delays | Low — author productivity impact | Medium | Start training in Phase 2; provide comprehensive documentation |
| jQuery dependency in shared components | Medium — header/footer rely on jQuery | High | Rebuild header/footer as vanilla JS blocks; no jQuery in EDS |

# 14. Recommended Team Composition

| Role | Count | Phase Allocation | Key Responsibilities |
| --- | --- | --- | --- |
| Technical Architect / Lead | 1 | P1-P3 | Integration design, block architecture, EDS patterns, technical decisions |
| Senior Frontend Developer | 2 | P1-P3 | Core block development, design system, responsive implementation |
| Frontend Developer | 2-3 | P1-P3 | Block development, CSS/JS, template implementation |
| Content Migration Engineer | 2 | P1-P3 | Import scripts, parsers, bulk migration tooling, content validation |
| Integration Developer | 1-2 | P1-P3 | Adobe Target, Analytics, Cart API, Auth, Chat, Search integration |
| QA Engineer | 1-2 | P2-P3 | Visual regression, accessibility, performance, cross-browser testing |
| Content Author / Editor | 1-2 | P2-P3 | Manual content review, content validation, author training |
| Project Manager | 1 | P1-P3 | Sprint planning, stakeholder communication, risk management |
| TOTAL | 11-15 | — | — |