Thermo Fisher Scientific

www.thermofisher.com

AEM AMS → Edge Delivery Services

Site Assessment & Migration Analysis Report

Prepared: March 15, 2026

CONFIDENTIAL

# Table of Contents

1. Executive Summary

2. Current Technology Stack

3. Integrations Analysis

4. Page & Asset Inventory

5. Templates Inventory

6. Blocks / Components Catalog

7. Page Counts by Template

8. Web Forms Analysis

9. Complex Use Cases & Observations

10. Analysis Summary

11. Migration Estimates

# 1. Executive Summary

Thermo Fisher Scientific (thermofisher.com) is one of the world's largest scientific services companies, with a complex web presence built on Adobe Experience Manager (AEM) Managed Services (AMS). This report provides a comprehensive analysis of the site for migration to Adobe Edge Delivery Services (EDS).

Key Findings:

- Total estimated URLs across all sitemaps: ~138,300+

- EDS migration scope (CMS content pages): ~31,200 pages across 39 locales

- Multiple technology stacks: AEM CMS, React SPA (commerce), WordPress (blog)

- 23 third-party integrations identified

- 35 unique blocks/components cataloged with 15+ design variations

- 11 distinct page templates identified

- 9 web form types across the site

- Estimated migration effort: 532-821 person-days (~6-9 months)

# 2. Current Technology Stack

The following table outlines the complete technology stack currently powering thermofisher.com:

| Layer | Technology | Details |
| --- | --- | --- |
| CMS | Adobe Experience Manager (AEM AMS) | AEM 6.5+, release/2025.9.0 - ETO |
| Frontend (CMS) | Vanilla JavaScript + jQuery Migrate 3.4.1 | No framework; custom Design System |
| Frontend (Commerce) | React + Redux | SPAs at /store/, /order/, /search/ |
| Frontend (Blog) | WordPress + jQuery | Genesis theme "accelerating-science" |
| CSS | Custom Design System + BEM | HelveticaNeue font stack, CSS custom properties |
| CDN | Akamai | Edge caching, TLS termination |
| Cloud | AWS (S3, ELB, Kubernetes) | Microservices orchestration |
| API Gateway | Apache APISIX (NGINX) | Request routing, rate limiting |
| Analytics | Adobe Experience Platform Web SDK (Alloy) v2.30.1 | Loaded via Adobe Launch |
| Tag Management | Adobe Launch (2 properties) | Build date: 2026-03-10 |
| Personalization | Adobe Target (via Alloy) | Server-side + client-side targeting |
| Identity | Custom OIDC + SAP Gigya | identity.thermofisher.com |
| Commerce | Custom .NET + K8s microservices | commerce.thermofisher.com |
| Search | Custom SearchBar v2023 + Lucidworks Solr | React SPA at /search/results |
| Consent | TrustArc | consent.truste.com |
| Responsive Breakpoints | 361px / 577px / 768px / 993px / 1201px / 1441px | 6 breakpoint system |

# 3. Integrations Analysis

The following third-party integrations and embedded services have been identified across the site:

| # | Integration | Type | Complexity | Where Used |
| --- | --- | --- | --- | --- |
| 1 | Adobe Experience Platform Web SDK | API/SDK | High | All pages |
| 2 | Adobe Launch (Tag Management) | Embed | Medium | All pages (2 properties) |
| 3 | Adobe Target | API/SDK | High | All pages - personalization, A/B testing |
| 4 | Adobe Audience Manager | API | Medium | All pages - audience segmentation |
| 5 | Akamai CDN | Infrastructure | Medium | All pages - edge caching |
| 6 | AWS S3 | API/Storage | Low | Static asset delivery |
| 7 | AWS ELB / Kubernetes | Infrastructure | High | Commerce microservices |
| 8 | SAP Gigya (Customer Data Cloud) | API/OAuth | High | Sign-in, registration |
| 9 | TrustArc | Embed/SDK | Medium | All pages - GDPR/CCPA consent |
| 10 | Medallia / Kampyle | Embed/SDK | Low | All pages - feedback overlay |
| 11 | Google reCAPTCHA v3 | API | Low | Password reset form |
| 12 | Genesys Cloud Chat | Embed/API | High | Category/product pages - AI chat |
| 13 | Custom Commerce API | Custom API | High | Cart, pricing, recommendations |
| 14 | Product Recommendations Engine | Custom API | High | Cart sidebar, product pages |
| 15 | Lucidworks Fusion / Solr | API | High | Search, autocomplete, typeahead |
| 16 | Custom OIDC Identity Provider | Custom API | High | Authentication flow, JWT tokens |
| 17 | Endeca (Search Focus Areas) | API | Medium | Faceted navigation |
| 18 | WordPress (Blog CMS) | Separate CMS | Medium | /blog/ - Accelerating Science |
| 19 | Magellan GenAI | Custom API | High | AI product Q&A (feature-flagged) |
| 20 | MasterControl | External Link | Low | Privacy policy document hosting |
| 21 | UserWay | Embed | Low | Accessibility overlay widget |
| 22 | Custom Digital Data Layer | Custom Code | Medium | All pages - analytics data layer |
| 23 | DM Preload Offers System | Custom Code | High | All pages - dynamic offer injection |

Integration Complexity Summary:

| Complexity | Count | Examples |
| --- | --- | --- |
| High | 12 | Adobe Target, Gigya Auth, Commerce API, Genesys Chat, Search |
| Medium | 6 | Adobe Launch, Audience Manager, TrustArc, Endeca, Digital Data Layer |
| Low | 5 | reCAPTCHA, Medallia, AWS S3, MasterControl, UserWay |

# 4. Page & Asset Inventory

Page counts were derived from analysis of 11 sitemap hierarchies declared in robots.txt:

| Category | Technology | Estimated URLs | In EDS Scope? |
| --- | --- | --- | --- |
| Regional CMS Content (39 sitemaps) | AEM CMS | ~31,200 | Yes - Primary |
| Store Product Catalog (239 sitemaps) | React SPA | ~47,800 | No - Separate SPA |
| Product FAQs (17 sitemaps) | React SPA | ~17,000 | No - Separate SPA |
| Product Citations (13 sitemaps) | React SPA | ~13,000 | No - Separate SPA |
| Antibody Products (16 sitemaps) | Custom App | ~14,750 | No - Separate App |
| Allergy Microsite (18 sitemaps) | AEM CMS | ~3,600 | Phase 2 |
| Clinical Mass Spec (17 sitemaps) | AEM CMS | ~1,275 | Phase 2 |
| One Lambda (1 sitemap) | AEM CMS | ~641 | Phase 2 |
| Binding Site (12 sitemaps) | AEM CMS | ~960 | Phase 2 |
| CAS Number Pages (6 sitemaps) | Custom App | ~570 | No - Separate App |
| Blog | WordPress | ~1,000-3,000 | No - Separate CMS |
| Antibody Video Sitemap | Mixed | ~7,500 | No - Video index |

Total Estimated URLs: ~138,300+

Phase 1 EDS Migration Scope: ~31,200 CMS content pages

Phase 2 EDS Migration Scope: ~6,476 microsite pages

## Estimated Digital Assets

| Asset Type | Estimated Count | Notes |
| --- | --- | --- |
| Product Images | ~500,000+ | Managed by PIM/DAM system; referenced via CDN |
| Marketing/Content Images | ~50,000-100,000 | AEM DAM - hero banners, category images, icons |
| PDF Documents | ~10,000-25,000 | SDS, CoA, protocols, datasheets, manuals |
| Video Assets | ~7,500+ | Hosted via video sitemap; YouTube/Vimeo embeds |
| SVG Icons | ~200-500 | UI icons, brand logos, navigation elements |
| Font Files | ~20-30 | HelveticaNeue variants (WOFF2) |

# 5. Templates Inventory

The following unique page templates have been identified across the site:

| # | Template Name | Complexity | Reasoning | Reference URL(s) |
| --- | --- | --- | --- | --- |
| 1 | Homepage | High | Heavy personalization (Adobe Target), dynamic carousels, multiple API integrations, hero with dynamic content | thermofisher.com/us/en/home.html |
| 2 | L1 Category Page | Medium | Multi-column category card grid, quick links, breadcrumbs, standard component layout | thermofisher.com/us/en/home/life-science.html |
| 3 | L2+ Category / Subcategory | Medium | Icon cards, value props, image+link layouts, deeper hierarchy | thermofisher.com/us/en/home/life-science/antibodies.html |
| 4 | Brand Page | Medium | Sidebar nav, anchor jump nav, multi-section link lists, resources section | thermofisher.com/us/en/home/brands/thermo-scientific.html |
| 5 | Product Detail Page (PDP) | High | React SPA, Redux state, real-time pricing, stock, citations, AI Q&A | thermofisher.com/order/catalog/product/44-2ML |
| 6 | Antibody Product Page | High | Separate custom app, specialized search, antibody data model | thermofisher.com/antibody/product/CD4-Antibody-... |
| 7 | Learning Center Hub | Medium | Educational modules, tutorial navigation, persistent learning menu | thermofisher.com/us/en/home/technical-resources/learning-centers.html |
| 8 | Support Hub | Medium | TOC navigation, expandable sections, multi-column link directory | thermofisher.com/us/en/home/support.html |
| 9 | Events / Webinars | Medium | Dynamic JS rendering, event registration, filters | thermofisher.com/us/en/home/events.html |
| 10 | Promotions | Medium | Adobe Target personalization, dynamic offer cards, geo-filtering | thermofisher.com/us/en/home/products-and-services/promotions.html |
| 11 | Contact / Forms | Medium | React-based rendering, multi-step forms, validation | thermofisher.com/us/en/home/technical-resources/contact-us.html |

## Template Screenshots

Homepage Template

L1 Category Template (Life Sciences)

L2 Category Template (Antibodies)

Brand Page Template (Thermo Scientific)

Support Hub Template

# 6. Blocks / Components Catalog

All reusable blocks and components identified across the site. Design variations of the same content model are grouped under a single block rather than listed as separate blocks.

## 6.1 Global Components

| # | Block Name | Complexity | Description | Variations | Reference URL |
| --- | --- | --- | --- | --- | --- |
| 1 | Header / Mega Navigation | High | Fixed header with multi-level mega-nav, search, account, cart, notifications, responsive drawer | Desktop mega-nav / Mobile drawer | All pages |
| 2 | Search Bar + Typeahead | High | Autocomplete with category provider selector, recent searches, signals tracking | Context-aware scope per page | All pages |
| 3 | Shopping Cart Sidebar | High | Right-sliding drawer with real-time cart, OOB recommendations API, pricing, quantity adjustment | Empty / Populated states | All pages |
| 4 | Footer (6-column) | Low | Multi-column link groups, legal bar, copyright, country selector with flag | None | All pages |
| 5 | Cookie Consent Banner | Medium | TrustArc GDPR/CCPA consent with preference management modal | None | All pages |
| 6 | Messaging Bar | Low | Sticky top promotional banner, dismissible, campaign-specific content | Content varies by campaign | All pages |
| 7 | Account Dropdown | Medium | Auth state-aware dropdown (guest sign-in vs. logged-in user details) | 2 states (guest / auth) | All pages |
| 8 | Notification Bell | Medium | Order update notifications, badge count, delete/clear actions | Empty / Populated | All pages |
| 9 | Chat Widget (Genesys) | High | AI-powered chat with eligibility API, async chunk-based loading | None (eligibility-gated) | Category/product pages |
| 10 | Feedback Tab | Low | Fixed "Give Feedback" tab triggering Medallia/Kampyle overlay | None | All pages |

## 6.2 Hero & Banner Components

| # | Block Name | Complexity | Description | Variations | Reference URL |
| --- | --- | --- | --- | --- | --- |
| 11 | Hero Banner / Teaser | Medium | Full-width hero with bg image, headline, body, CTA. Supports Adobe Target personalization | Static / Dynamic (personalized) | Homepage |
| 12 | Promotional Tile Strip (3-up) | Low | Row of 3 small promotional tiles with icon, short copy, CTA link | None | Homepage |

## 6.3 Navigation Components

| # | Block Name | Complexity | Description | Variations | Reference URL |
| --- | --- | --- | --- | --- | --- |
| 13 | Breadcrumbs | Low | Hierarchical path nav with ">" separator, last item plain text | Depth varies by page level | All non-homepage pages |
| 14 | Sidebar Navigation | Low | Left-column categorized link lists (Popular products, Key apps, Resources) | Content varies by brand | Brand pages |
| 15 | Anchor / Jump Navigation | Low | Horizontal in-page hash anchors with "Top" back-links | Items vary by content | Brand pages |
| 16 | Quick Links Row | Low | Horizontal row of popular product links | Content varies per category | L1 Category pages |
| 17 | Table of Contents (Collapsible) | Medium | Expandable section navigator for support/reference content | None | Support pages |

## 6.4 Content Components

| # | Block Name | Complexity | Description | Variations | Reference URL |
| --- | --- | --- | --- | --- | --- |
| 18 | Category Card Grid | Low | Grid of heading+description cards for subcategories (4-column responsive) | None | L1 Category pages |
| 19 | Icon Link Cards (4-up) | Low | Row of 4 icon+label navigation cards for sub-categories | None | L2 Category pages |
| 20 | Value Proposition Cards (3-up) | Low | Feature cards with icon/number, heading, description, CTA | None | L2 Category pages |
| 21 | Image + Link List (Split) | Low | Large image with adjacent application link columns | Image left / Image right | L2 Category pages |
| 22 | Link Grid (3-col with icons) | Low | Three-column icon+text link grid for research areas | None | L2 Category pages |
| 23 | Resource Card Row | Low | Cards with thumbnail, title, description, CTA. Horizontal or vertical layout | Horizontal / Vertical | Multiple pages |
| 24 | Text Block (Rich Text) | Low | Standard heading + paragraph content with inline links | Various heading levels | All pages |
| 25 | Section Divider | Low | Styled horizontal rule between content sections | None | Multiple pages |
| 26 | Categorized Link Lists (2-col) | Low | Two-column bulleted link sections under heading | None | Brand pages |
| 27 | Resource Section + Thumbnails | Low | Boxed section with 3 resource cards (70x70 thumbnail) + link list | None | Brand pages |

## 6.5 E-Commerce Components

| # | Block Name | Complexity | Description | Variations | Reference URL |
| --- | --- | --- | --- | --- | --- |
| 28 | Online Offers Grid (4-up) | Medium | Product cards with pricing, discount badge, add-to-cart, pagination | None | Homepage |
| 29 | Promotion Card Grid (2x2) | Low | Promo cards with image, discount badge overlay, CTA | Badge style varies | Homepage, Support |
| 30 | New Products Row (3-up) | Low | Product feature cards with image, title, description, CTA | None | Homepage |
| 31 | Suggested Products (Cross-sell) | Medium | API-driven recommendation strip in cart sidebar | None | All pages (in cart) |

## 6.6 Interactive & Utility Components

| # | Block Name | Complexity | Description | Variations | Reference URL |
| --- | --- | --- | --- | --- | --- |
| 32 | CTA Button | Low | Multi-variant button/link: primary(red), secondary, outline, info, white, text-link | 6+ visual variants, 4 sizes | All pages |
| 33 | Blog Post Cards (3-up) | Low | Blog cards with thumbnail, title, date, "Read more" CTA | None | Homepage |
| 34 | Featured Education Section | Medium | Mixed content tiles - interactive tool cards + simple text cards | Mixed content types | Homepage |
| 35 | Preload Offers Engine | High | Adobe Target dynamic content injection framework with fallback handling | Default / Personalized | All pages |

# 7. Page Counts by Template

| # | Template | Est. Pages | Auto-Migrate | Manual Migrate | Notes |
| --- | --- | --- | --- | --- | --- |
| 1 | Homepage | ~38 | No | Yes (100%) | 1 per locale, heavy personalization |
| 2 | L1 Category Pages | ~800-1,200 | Partial (70%) | Partial (30%) | Standard layout; dynamic offers manual |
| 3 | L2+ Category / Subcategory | ~15,000-25,000 | Yes (90%) | ~10% manual | US-EN industrial alone = 1,031 URLs |
| 4 | Brand Pages | ~300-450 | Yes (85%) | ~15% manual | ~12 brands x 39 locales |
| 5 | Product Detail (React SPA) | ~47,800 | Out of Scope | Out of Scope | Separate React application |
| 6 | Antibody Product Pages | ~14,750 | Out of Scope | Out of Scope | Separate custom application |
| 7 | Learning Center Hubs | ~100-200 | Partial (50%) | Yes (50%) | Educational content modules |
| 8 | Support Hub | ~50-100 | No | Yes (100%) | Dynamic expandable content |
| 9 | Events / Webinars | ~50-100 | No | Yes (100%) | JS-heavy dynamic rendering |
| 10 | Promotions | ~50-100 | No | Yes (100%) | Adobe Target personalization |
| 11 | Contact / Forms | ~100-200 | No | Yes (100%) | React-based forms |

Migration Scope Summary:

| Category | Pages | Strategy |
| --- | --- | --- |
| Automatically Migratable | ~18,000-28,000 | Standard templates, batch processing |
| Manual Migration Required | ~4,000-7,000 | Dynamic, personalized, custom logic |
| Out of Scope (Separate Apps) | ~97,000+ | React SPA, WordPress, custom apps |
| Phase 1 Total | ~31,200 | CMS content pages across 39 locales |

# 8. Web Forms Analysis

Analysis of all pages capturing user input via form controls:

| # | Form Name | Location | Complexity | Reasoning |
| --- | --- | --- | --- | --- |
| 1 | Quick Order (Multi-Mode) | /store/v2/quick-order | High | 3 input modes (manual/bulk/paste), dynamic autocomplete, conditional fields, dynamic rows, cart API |
| 2 | Return / Report Issue | /store/order/report/issues | High | 15+ fields, 5 sections, cascading dropdowns, drag-drop file upload, conditional validation |
| 3 | Sign-In (Multi-Step Auth) | identity.thermofisher.com/signin | Medium | Multi-step OAuth/OIDC, Gigya integration, JWT tokens |
| 4 | Account Registration | identity.thermofisher.com/registration | Medium | Gigya-managed, password strength meter, country selector, reCAPTCHA |
| 5 | Contact Us Form | /store/v2/contact-us | Medium | React SPA, multi-section layout, validation, file attachment |
| 6 | Global Site Search | Header (all pages) | Medium | Advanced autocomplete, category filtering, signals capture |
| 7 | Password Reset | identity.thermofisher.com/reset-password | Low | Single field + reCAPTCHA v3 |
| 8 | Feedback (Medallia) | Footer "Report a Site Issue" | Low | Third-party managed overlay (Kampyle SDK) |
| 9 | Add to Cart / Quantity | Product detail pages | Low | Single numeric spinbutton + "Add to Cart" button |

Forms Complexity Summary:

| Complexity | Count | Forms |
| --- | --- | --- |
| High | 2 | Quick Order, Return/Report Issue |
| Medium | 4 | Sign-In, Registration, Contact Us, Site Search |
| Low | 3 | Password Reset, Feedback (Medallia), Add to Cart |

Note: Legacy standalone form URLs (/global/forms/inquiry.html, /global/forms/sample-request.html, /global/forms/quote-request.html, /global/forms/newsletter-signup.html) all return 404 — Thermo Fisher has consolidated forms into JavaScript-rendered experiences within the /store/v2/ framework.

# 9. Complex Use Cases & Observations

The following complex behaviors require special attention during migration:

| # | Complex Use Case | Instances | Where Found | Why Complex |
| --- | --- | --- | --- | --- |
| 1 | Adobe Target Personalization | ~31,200+ pages | Preload Offers system on every page | Dynamic content varies by user segment, geography, behavior. EDS lacks native server-side personalization at this scale. |
| 2 | React SPA Commerce | ~78,000+ pages | /order/, /store/, /search/ | Separate React apps with Redux. NOT AEM pages — need independent architecture or continued SPA operation. |
| 3 | Multi-Locale Content (39 locales) | 39 locale variants | All CMS pages | Content translation, country-specific pricing, regional compliance (GDPR vs CCPA). Robust locale management needed. |
| 4 | Dynamic Cart Integration | All pages | Cart sidebar, OOB recommendations API | Real-time cart state synced across all pages via API. Requires client-side JS integration with custom commerce APIs. |
| 5 | Custom Authentication (OIDC+Gigya) | All auth flows | identity.thermofisher.com | Custom identity provider with OIDC, JWT. Contracted pricing, order history depend on auth state. |
| 6 | AI-Powered Features (Magellan) | Product/Search pages | Feature-flagged globally | Semantic search, AI product Q&A in testing. Rapidly evolving; may change during migration. |
| 7 | Genesys Cloud Chat Bot | ~5,000+ pages | Category & product pages | AI chat with eligibility API. Async loading, chunk-based JS/CSS, and API integration. |
| 8 | Dynamic Offer System | All pages | window.preloadOffers | Client-side Adobe Target content injection with timeout/fallback. Drives hero banners, offer bars, promotions. |
| 9 | Sub-sites (Separate Templates) | 3 sub-sites | Allergy, One Lambda, Binding Site | Separate AEM content trees, independent nav/branding. Need separate EDS configs. |
| 10 | E-commerce Pricing & Stock | Product pages | Pricing & stock APIs | Real-time pricing, inventory, contracted pricing, multi-currency. Critical for buyer experience. |

# 10. Analysis Summary

| Category | Count | Low | Medium | High |
| --- | --- | --- | --- | --- |
| Page Templates | 11 | 0 | 7 | 4 |
| Blocks / Components | 35 | 20 | 9 | 6 |
| Design Variations | ~15 | 10 | 4 | 1 |
| Third-Party Integrations | 23 | 5 | 6 | 12 |
| Web Forms | 9 | 3 | 4 | 2 |
| Complex Use Cases | 10 | 0 | 3 | 7 |

Site Scale Overview:

| Metric | Value |
| --- | --- |
| Total Estimated URLs (all sitemaps) | ~138,300+ |
| CMS Content Pages (EDS Phase 1 Scope) | ~31,200 |
| Microsite Pages (EDS Phase 2 Scope) | ~6,476 |
| Product Catalog (React SPA - separate) | ~77,800 |
| Antibody Products (Custom app - separate) | ~14,750 |
| Blog (WordPress - separate) | ~1,000-3,000 |
| Locales | 39 |
| Estimated DAM Assets (images) | ~50,000-100,000 |
| Estimated PDF Documents | ~10,000-25,000 |

# 11. Migration Estimates

## Scope Definition

The EDS migration scope covers AEM CMS content pages only (~31,200 pages in Phase 1). React commerce SPA, WordPress blog, and antibody application remain as separate systems operating independently.

## Effort Breakdown by Phase

| Phase | Activity | Person-Days (Range) | Calendar Duration |
| --- | --- | --- | --- |
| Phase 1 | Foundation & Setup |  |  |
|  | EDS project setup, CI/CD, environments | 5-10 | 1 week |
|  | Design system extraction & CSS custom properties | 15-20 | 2 weeks |
|  | Global header / mega-navigation | 15-25 | 2-3 weeks |
|  | Global footer | 3-5 | 1 week |
|  | Cookie consent (TrustArc) integration | 3-5 | 1 week |
|  | Phase 1 Subtotal | 41-65 | 3-4 weeks |
| Phase 2 | Block Development |  |  |
|  | Low-complexity blocks (20 blocks × 2-3 days) | 40-60 |  |
|  | Medium-complexity blocks (9 blocks × 5-8 days) | 45-72 |  |
|  | High-complexity blocks (6 blocks × 10-15 days) | 60-90 |  |
|  | Design variations (15 variants × 1-1.5 days) | 15-22 |  |
|  | Phase 2 Subtotal | 160-244 | 8-12 weeks |
| Phase 3 | Template Implementation |  |  |
|  | Homepage template | 10-15 |  |
|  | Category templates (L1 + L2) | 10-15 |  |
|  | Brand page template | 5-8 |  |
|  | Learning center, Support, Events, Promos | 15-23 |  |
|  | Contact/Forms template | 5-8 |  |
|  | Phase 3 Subtotal | 48-74 | 3-5 weeks |
| Phase 4 | Integrations |  |  |
|  | Adobe Analytics / Launch integration | 10-15 |  |
|  | Adobe Target / personalization | 15-25 |  |
|  | Commerce API integration (cart, pricing) | 15-20 |  |
|  | Authentication (OIDC/Gigya) | 10-15 |  |
|  | Search integration | 10-15 |  |
|  | Chat, Medallia, UserWay, reCAPTCHA | 10-16 |  |
|  | Phase 4 Subtotal | 70-106 | 4-6 weeks |
| Phase 5 | Content Migration |  |  |
|  | Migration script development & testing | 15-20 |  |
|  | Automated migration (~18,000-28,000 pages) | 20-30 |  |
|  | Manual migration (~4,000-7,000 pages) | 40-70 |  |
|  | Multi-locale content (39 locales) | 20-30 |  |
|  | Asset migration (images, documents) | 10-15 |  |
|  | Phase 5 Subtotal | 105-165 | 5-8 weeks |
| Phase 6 | Forms Migration |  |  |
|  | Low-complexity forms (3) | 3-5 |  |
|  | Medium-complexity forms (4) | 12-20 |  |
|  | High-complexity forms (2) | 10-16 |  |
|  | Phase 6 Subtotal | 25-41 | 2-3 weeks |
| Phase 7 | QA & Testing |  |  |
|  | Visual regression testing | 15-25 |  |
|  | Functional testing | 15-20 |  |
|  | Performance testing (Lighthouse 100) | 10-15 |  |
|  | Accessibility testing (WCAG 2.1 AA) | 10-15 |  |
|  | UAT support | 10-15 |  |
|  | Phase 7 Subtotal | 60-90 | 4-6 weeks |
| Phase 8 | Deployment & Cutover |  |  |
|  | Staging environment & validation | 5-8 |  |
|  | Redirect mapping (URL mapping) | 10-15 |  |
|  | DNS / CDN cutover planning | 3-5 |  |
|  | Go-live support & monitoring | 5-8 |  |
|  | Phase 8 Subtotal | 23-36 | 2-3 weeks |

## Total Estimates Summary

| Category | Person-Days (Range) | Calendar Duration |
| --- | --- | --- |
| Phase 1: Foundation & Setup | 41-65 | 3-4 weeks |
| Phase 2: Block Development | 160-244 | 8-12 weeks |
| Phase 3: Template Implementation | 48-74 | 3-5 weeks |
| Phase 4: Integrations | 70-106 | 4-6 weeks |
| Phase 5: Content Migration | 105-165 | 5-8 weeks |
| Phase 6: Forms Migration | 25-41 | 2-3 weeks |
| Phase 7: QA & Testing | 60-90 | 4-6 weeks |
| Phase 8: Deployment & Cutover | 23-36 | 2-3 weeks |
| TOTAL | 532-821 person-days | ~6-9 months (parallel phases) |

## Recommended Team Composition

| Role | Count | Focus Area |
| --- | --- | --- |
| Technical Lead / Architect | 1 | Architecture, integration design, decisions |
| Senior EDS Developer | 2-3 | Block development, template implementation |
| Frontend Developer | 2-3 | CSS/design system, responsive, a11y |
| Content Migration Engineer | 1-2 | Import scripts, batch processing, validation |
| QA Engineer | 1-2 | Automated testing, visual regression, performance |
| Integration Developer | 1 | Adobe Target, analytics, commerce APIs, auth |

Recommended team size: 8-12 people

## Key Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Personalization complexity (Adobe Target) | High | Plan edge-based personalization early; use EDS experimentation features |
| Commerce SPA dependency | High | Keep React SPA separate; integrate via client-side JS |
| 39-locale content volume | High | Automate batch processing; prioritize top 5-10 locales for initial launch |
| Custom identity system | Medium | Plan auth integration early; may require token relay proxy |
| AI features rapidly evolving | Medium | Feature-flag based integration; expect changes during migration |
| Blog (WordPress) separate CMS | Low | Maintain as-is or plan separate migration project |

— End of Report —