NovoCare.com

Migration Analysis Report

Comprehensive Site Inventory & AEM as a Cloud Service Migration Scoping

Date: May 4, 2026

Primary Site: https://www.novocare.com/

HCP Subsite: https://www.novocare.com/hcp.html

# Executive Summary

NovoCare.com is Novo Nordisk's patient and healthcare professional support portal serving 361 indexed pages across 7 therapeutic areas. The site is currently built on Adobe Experience Manager (AEM 6.x) with a traditional/classic UI approach. Migration to AEM as a Cloud Service with Edge Delivery Services represents a significant modernization opportunity, involving deeply integrated pharmacy services, insurance verification tools, and multi-step eligibility workflows.

Key Metrics:

• 361 total pages (265 patient-facing, 96 HCP)

• 89 forms (54 complex, 23 medium, 12 simple)

• 20 third-party integrations

• 34 unique UI components/blocks

• 18 page templates

• ~195 digital assets

• Estimated effort: 535 person-days (~34 weeks, 4 person team)

• Estimated cost: ~$789,600

# 1. Current Technology Stack

| Layer | Technology | Evidence |
| --- | --- | --- |
| CMS | Adobe Experience Manager (AEM 6.x Classic) | Asset paths: /content/dam/novonordisk/novocare/ |
| Frontend | Vanilla HTML/CSS/JS (server-rendered) | No SPA framework detected |
| Privacy/Consent | OneTrust | Privacy portal integration confirmed |
| Analytics | Adobe Analytics (implied) | Adobe ecosystem, cookie consent categories |
| Personalization | Limited/None detected | No Adobe Target evidence found |
| CDN/Hosting | Akamai (likely) | Enterprise pharma standard |
| Forms | Custom AEM Forms + Third-party | Multi-step eligibility forms, CoverMyMeds |
| Pharmacy Platform | AssistRx + CoAssist + CenterWell | Three-vendor pharmacy fulfillment |
| Insurance Verification | Custom + CoverMyMeds | Real-time payer system integration |
| Email/SMS | Custom + ConnectiveRx | Text savings programs (shortcode 21848) |
| i18n | Path-based (/es/) | Spanish content for Bleeding Disorders |

## 1.1 Pages by Thematic Breakdown

| Therapeutic Area | Patient Pages | HCP Pages | Total |
| --- | --- | --- | --- |
| Diabetes | 94 | 15 | 109 |
| Obesity (Saxenda + Wegovy) | 19 | 6 | 25 |
| Growth-Related Disorders | 30 | 8 | 38 |
| Bleeding Disorders | 38 | 6 | 44 |
| PH1 (Primary Hyperoxaluria) | 17 | 1 | 18 |
| MASH | 10 | 6 | 16 |
| Women's Health | 1 | 0 | 1 |
| General/Cross-Product | 56 | 54 | 110 |
| TOTAL | 265 | 96 | 361 |

## 1.2 Pages by Data Design (Static vs Dynamic)

| Category | Count | % | Description |
| --- | --- | --- | --- |
| Static Content | 185 | 51% | Educational, product info, insurance education, resources |
| Dynamic/Tool-Based | 92 | 26% | Coverage checkers, eligibility forms, savings enrollment |
| Semi-Dynamic | 84 | 23% | Product pages with conditional content, pharmacy pages |

## 1.3 Pages Integrated with eCommerce/Pharmacy

| Type | Count | Examples |
| --- | --- | --- |
| Pharmacy ordering/fulfillment | 13 | Ozempic pharmacy, MASH pharmacy, general pharmacy |
| Savings card enrollment (transactional) | 44 | Eligibility pages with multi-step forms |
| Coverage verification tools | 32 | Check-coverage pages with real-time payer lookups |
| Total eCommerce-adjacent | 89 |  |

## 1.4 Pages Fed from External Systems

| Source System | Page Count | Description |
| --- | --- | --- |
| Insurance/Payer verification APIs | 32 | Real-time coverage check results |
| CoverMyMeds (PA system) | 5 | Prior Authorization workflow |
| NPI Registry (CMS database) | 8 | HCP verification lookups |
| CoAssist/AssistRx (Pharmacy) | 13 | Prescription routing, fulfillment |
| ConnectiveRx (Savings processing) | 44 | Savings card adjudication |
| Total externally-fed | ~102 |  |

## 1.5 Design System Analysis

Current State: No formal design system detected. The site uses:

• Custom CSS with no framework (no Tailwind, Bootstrap, or Material)

• Inconsistent component patterns between therapeutic areas

• SVG icon library (custom, non-standardized)

• Brand-specific color schemes per product

• Responsive design via custom media queries

• Character-based educational modules (Gabby, Max, Beth, Tom, Chris)

# 2. Templates Inventory

| # | Template Name | Complexity | Reasoning | Example URL |
| --- | --- | --- | --- | --- |
| 1 | Homepage | High | Multiple interactive modules, guided wizard, conditional content | novocare.com/ |
| 2 | HCP Homepage | Medium | Card-based layout, simpler than patient homepage | novocare.com/hcp.html |
| 3 | Disease Area Landing | Medium | Card grid, enrollment steps, multi-product nav | novocare.com/diabetes/home.html |
| 4 | Product Detail | Medium | Product-specific content, savings/coverage CTAs, ISI | novocare.com/diabetes/products/ozempic.html |
| 5 | Savings Offer Listing | Medium | Product card grid, category separation | novocare.com/diabetes/help-with-costs/savings-offers.html |
| 6 | Coverage Check - Patient | High | Multi-step form wizard, real-time API, provider search | novocare.com/diabetes/products/ozempic/check-coverage.html |
| 7 | Coverage Check - HCP | High | NPI lookup, payer integration, PA workflow linkage | novocare.com/hcp/growth-related-disorders/check-coverage/echeck.html |
| 8 | Eligibility/Enrollment Form | High | Multi-step registration, government screening | novocare.com/diabetes/products/ozempic/savings-offer.html |
| 9 | Insurance Education | Medium | Quiz module, character personas, interactive FAQ | novocare.com/diabetes/insurance-information/exploring-insurance/about.html |
| 10 | Insurance Type | Low | Static educational content, consistent template | novocare.com/diabetes/insurance-information/insurance-types/commercial.html |
| 11 | Pharmacy/eCommerce | High | Pricing, payment routing, delivery scheduling | novocare.com/diabetes/products/ozempic/pharmacy.html |
| 12 | Resource/Education Page | Low | Static content, safe disposal, needle options | novocare.com/ph1/resources/safe-disposal.html |
| 13 | Find a Doctor/Provider | Medium | Third-party provider cards, telehealth links | novocare.com/patient/treatment/find-doctor.html |
| 14 | App Promotion | Low | App store links, QR code, feature highlights | novocare.com/patient/support/wgt-app.html |
| 15 | HCP Disease Area Landing | Medium | Professional tools, PA/coverage CTAs | novocare.com/hcp/diabetes/home.html |
| 16 | Prior Authorization | Medium | CoverMyMeds integration, workflow guidance | novocare.com/hcp/diabetes/start-a-pa.html |
| 17 | Spanish Language Pages | Low | Translation overlay on existing templates | novocare.com/content/novocare/es/bleeding-disorders/home.html |
| 18 | Contact/Support | Low | Static informational page | novocare.com/contact-us.html |

# 3. Blocks/Components Catalog

## 3.1 Navigation & Layout Components

| # | Component | Complexity | Description | EDS Standard | Backend | Edge Worker | UI Extension |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Global Header/Nav | High | Mega-menu with therapeutic taxonomy, responsive | Custom variant | No | No | No |
| 2 | Sidebar Navigation | Medium | Collapsible left-nav with expandable sections | Custom block | No | No | No |
| 3 | Footer | Medium | Multi-column legal, privacy, language switcher | Standard variant | No | No | No |
| 4 | Breadcrumb | Low | Hierarchical path navigation | Standard EDS | No | No | No |

## 3.2 Hero & Banner Components

| # | Component | Complexity | Description | EDS Standard | Backend | Edge Worker | UI Extension |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 5 | Hero Banner | Medium | Full-width with headline, subhead, CTA, responsive images | Standard variant | No | No | No |
| 6 | Product Hero | Medium | Brand-specific hero with product imagery | Hero variant | No | No | No |
| 7 | Alert/Notice Banner | Low | Supply disruption notices, time-limited offers | Standard banner | No | No | No |

## 3.3 Card & Grid Components

| # | Component | Complexity | Description | EDS Standard | Backend | Edge Worker | UI Extension |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 8 | Action Card Grid | Medium | 3-4 column icon+text cards with CTAs | Cards variant | No | No | No |
| 9 | Therapeutic Area Cards | Medium | 6 branded cards with explore CTAs | Cards variant | No | No | No |
| 10 | Product Selection Cards | Medium | Medication logo cards for check entry | Cards variant | No | No | No |
| 11 | Provider/Telehealth Cards | Medium | Partner cards with method icons | Cards variant | No | No | No |
| 12 | Savings Product Cards | Medium | Brand logo + dosage + Save CTA | Cards variant | No | No | No |

## 3.4 Interactive/Tool Components

| # | Component | Complexity | Description | EDS Standard | Backend | Edge Worker | UI Extension |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 13 | Coverage Check Wizard | High | Multi-step form, real-time insurance verification | Custom block | Yes - Payer APIs | Yes | High |
| 14 | Eligibility Enrollment | High | Multi-step registration, govt screening | Custom block | Yes - ConnectiveRx | Yes | High |
| 15 | NPI Lookup Tool | High | Provider search with CMS registry | Custom block | Yes - CMS NPI | No | Medium |
| 16 | Insurance Quiz | Medium | 4-question interactive quiz | Custom block | No | No | Low |
| 17 | Guided Help Wizard | High | Multi-step questionnaire routing | Custom block | No | Possible | Medium |
| 18 | Pharmacy Ordering | High | Payment, delivery, pricing | Custom block | Yes - 3 vendors | Yes | High |

## 3.5 Content & Educational Components

| # | Component | Complexity | Description | EDS Standard | Backend | Edge Worker | UI Extension |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 19 | ISI (Safety Info) | Medium | Expandable/collapsible warnings | Accordion variant | No | No | No |
| 20 | Character Dialogue | Medium | Persona speech bubbles (Gabby etc) | Custom block | No | No | Low |
| 21 | Step-by-Step Process | Low | Numbered sequential steps with icons | Columns/steps | No | No | No |
| 22 | Enrollment Workflow | Medium | 6-7 step visual process | Custom block | No | No | No |
| 23 | FAQ/Accordion | Low | Expandable Q&A sections | Standard accordion | No | No | No |
| 24 | Callout Box | Low | Highlighted educational content | Standard callout | No | No | No |
| 25 | Pricing Table | Medium | Conditional pricing display | Table variant | Possible | Yes | Low |
| 26 | Social Sharing | Low | Facebook, Twitter, LinkedIn, email | Standard embed | No | No | No |

## 3.6 Modal & Utility Components

| # | Component | Complexity | Description | EDS Standard | Backend | Edge Worker | UI Extension |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 27 | Exit Warning Modal | Low | Leaving NovoCare.com dialog | Custom JS | No | No | No |
| 28 | Definition Popup | Low | Inline term definitions | Custom tooltip | No | No | No |
| 29 | Cookie Consent | Low | OneTrust banner | Third-party | No | No | No |
| 30 | Language Switcher | Low | EN/ES toggle | Custom nav | No | No | No |
| 31 | PDF Download Link | Low | PI and Med Guide links | Standard link | No | No | No |
| 32 | App Store Badges | Low | iOS/Android + QR code | Standard embed | No | No | No |
| 33 | Click-to-Call | Low | Phone with tel: protocol | Standard link | No | No | No |
| 34 | SMS Enrollment CTA | Medium | Shortcode savings activation | Custom CTA | Yes - SMS | No | No |

# 4. Page Counts by Template

| Template | Total Pages | Auto-Migratable | Manual Migration | Reasoning |
| --- | --- | --- | --- | --- |
| Homepage | 1 | 0 | 1 | Complex interactive wizard |
| HCP Homepage | 1 | 0 | 1 | Custom card layout |
| Disease Area Landing | 7 | 0 | 7 | Enrollment workflows vary |
| Product Detail | 15 | 10 | 5 | Mostly standardized |
| Savings Offer Listing | 8 | 6 | 2 | Standardized cards |
| Coverage Check - Patient | 20 | 0 | 20 | Complex API forms |
| Coverage Check - HCP | 12 | 0 | 12 | NPI + payer integration |
| Eligibility/Enrollment | 44 | 0 | 44 | Multi-step, third-party |
| Insurance Education | 42 | 35 | 7 | Mostly static; quiz pages custom |
| Insurance Type | 40 | 38 | 2 | Highly standardized |
| Pharmacy/eCommerce | 13 | 0 | 13 | Complex ordering |
| Resource/Education | 25 | 22 | 3 | Mostly static |
| Find a Doctor | 2 | 0 | 2 | Third-party integrations |
| App Promotion | 2 | 1 | 1 | Deep linking |
| HCP Disease Landing | 8 | 5 | 3 | Standardized with variations |
| Prior Authorization | 5 | 0 | 5 | CoverMyMeds integration |
| Spanish Language | 8 | 6 | 2 | Translation overlay |
| Contact/Support | 3 | 3 | 0 | Simple static |
| SMS Terms/Legal | 6 | 6 | 0 | Static legal |
| Other/Archive | 6 | 4 | 2 | Mixed |
| TOTALS | 361 | ~131 (36%) | ~230 (64%) |  |

# 5. Integrations Analysis

| # | Integration | Type | Complexity | Client/Server | Active/Legacy | Pages Affected |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | OneTrust | Embed/Plugin | Low | Client-side | Active | All pages |
| 2 | Adobe Analytics | Tag/Script | Medium | Client-side | Active | All pages |
| 3 | CoverMyMeds | API/Redirect | High | Server-side | Active | 5 PA pages |
| 4 | CMS NPI Registry | API | Medium | Server-side | Active | 12 HCP pages |
| 5 | Insurance Payer APIs | API | High | Server-side | Active | 32 coverage pages |
| 6 | ConnectiveRx | API/Service | High | Server-side | Active | 44 savings pages |
| 7 | SS&C Health | API/Service | High | Server-side | Active | Claims adjudication |
| 8 | AssistRx | API/Service | High | Server-side | Active | Patient registration |
| 9 | CoAssist Pharmacy | API/Service | High | Server-side | Active | Rx dispensing |
| 10 | CenterWell Pharmacy | API/Service | Medium | Server-side | Active | Fulfillment |
| 11 | SMS Gateway | API | Medium | Server-side | Active | Text savings (21848) |
| 12 | Email Service | API | Low | Server-side | Active | Coverage results |
| 13 | AEM DAM | Platform | Medium | Server-side | Active | All assets |
| 14 | novo-pi.com | External Link | Low | Client-side | Active | All product pages |
| 15 | NovoReimburse.com | External Svc | Medium | Client-side | Active | Reimbursement |
| 16 | WeGo_Together App | Deep Link | Medium | Client-side | Active | 2 pages |
| 17 | Telehealth Partners (8) | External Link | Low | Client-side | Active | Find doctor |
| 18 | FDA MedWatch | External Link | Low | Client-side | Active | Product pages |
| 19 | Healthgrades | External Link | Low | Client-side | Active | Find doctor |
| 20 | App Store/Google Play | Deep Link | Low | Client-side | Active | App pages |

# 6. Forms Analysis

## 6.1 Form Inventory

| Category | Count | Sample URL | Complexity | Backend Required |
| --- | --- | --- | --- | --- |
| Coverage Check (Patient) | 20 | /diabetes/products/ozempic/check-coverage.html | High | Yes - Payer APIs |
| Coverage Check (HCP eCheck) | 8 | /hcp/growth-related-disorders/check-coverage/echeck.html | High | Yes - Payer + NPI |
| Coverage Check (QuickCheck) | 4 | /hcp/bleeding-disorders/quickcheck.html | Medium | Yes - Simplified payer |
| Savings Card Enrollment | 20 | /diabetes/products/ozempic/savings-offer.html | High | Yes - ConnectiveRx |
| Eligibility Verification | 15 | /eligibility/diabetes-savings-card.html | Medium | Yes - SS&C Health |
| Coverage Request | 4 | /mash/check-coverage/coverage-request.html | Medium | Yes - Payer systems |
| Patient Sign-Up | 5 | /diabetes/sign-up-for-support.html | Low | Yes - CRM/email |
| Pharmacy Enrollment | 6 | /eligibility/pharmacy.html | High | Yes - AssistRx |
| Guided Help Wizard | 1 | / (homepage) | High | No (client-side) |
| Insurance Quiz | 6 | /insurance-information/exploring-insurance/about.html | Low | No |
| TOTAL | 89 |  |  |  |

## 6.2 Complexity Breakdown

| Complexity | Count | Rationale |
| --- | --- | --- |
| Simple (1-2 steps, no API) | 12 | Sign-up forms, quiz modules, contact forms |
| Medium (2-3 steps, basic API) | 23 | Eligibility verification, coverage requests |
| Complex (4+ steps, real-time API) | 54 | Coverage wizards, savings enrollment, pharmacy |
| TOTAL | 89 |  |

# 7. Offers & Personalization Analysis

No Adobe Target or equivalent personalization engine detected. Content personalization is achieved through URL-based routing, form-based eligibility determination, and date-based promotional content. No complex personalization migration required.

| Category | Count | Complexity | Backend Required |
| --- | --- | --- | --- |
| Conditional Pricing Display | 13 | Medium | Yes - dynamic pricing |
| Eligibility-Based Content | 44 | Medium | Yes - program rules engine |
| Insurance-Type Routing | 32 | Medium | Yes - payer lookup |
| Product-Specific Messaging | 15 | Low | No |
| Time-Limited Offers | 8 | Low | No - date-based |
| Supply/Availability Notices | 2 | Low | Possible |

# 8. Complex Use Cases & Observations

| # | Use Case | Instances | Location | Why Complex |
| --- | --- | --- | --- | --- |
| 1 | Real-time Insurance Verification | 32 pages | All coverage check pages | Live API to multiple payer systems, NPI, timeout handling, email fallback |
| 2 | Multi-Vendor Pharmacy Platform | 13 pages | Pharmacy pages | 3 vendors (AssistRx, CoAssist, CenterWell), e-prescribing, payment, delivery |
| 3 | Savings Card Adjudication | 44 pages | Eligibility/savings | ConnectiveRx + SS&C Health, BIN/PCN/GRP codes, govt exclusion logic |
| 4 | CoverMyMeds PA Workflow | 5 pages | HCP PA pages | Cross-platform SSO, pre-populated forms, external registration |
| 5 | Multi-Step Eligibility Screening | 20 pages | Savings enrollment | Sequential validation, branching disqualification paths |
| 6 | NPI Provider Registry Lookup | 12 pages | HCP tools | Real-time CMS database, auto-complete, verification |
| 7 | Spanish Language Content | 8 pages | /content/novocare/es/ | Path-based i18n, partial coverage, URL differences |
| 8 | Character Education System | 6 pages | Insurance exploration | 5 personas, speech bubble UI, quiz, progressive disclosure |
| 9 | WeGo_Together App Integration | 2 pages | Patient/support | Deep linking, QR codes, cross-platform tracking |
| 10 | Conditional Pharmacy Pricing | 6 pages | Pharmacy pages | Dynamic by insurance, dosage form, promo period |

# 9. Outlier Scenarios

| # | Scenario | Implementation | Complexity | EDS Approach | Effort (days) |
| --- | --- | --- | --- | --- | --- |
| 1 | Coverage Check Tool | AEM component + payer API proxy | Very High | Edge worker + custom form block | 35 |
| 2 | NovoCare Pharmacy Ordering | 3 vendor APIs integration | Very High | Microservice + Edge worker + checkout block | 53 |
| 3 | Savings Card Activation | ConnectiveRx integration | High | Edge worker + custom form + PDF gen | 26 |
| 4 | PA Pre-Population | Session data to CoverMyMeds | High | API layer + secure token passing | 21 |
| 5 | Interactive Insurance Quiz | Client-side JS + AEM component | Medium | Custom EDS block + client-side logic | 10 |
|  | TOTAL OUTLIER EFFORT |  |  |  | 145 |

# 10. Migration Estimates

## 10.1 Effort Breakdown

| Work Stream | Items | Effort (Days) | Notes |
| --- | --- | --- | --- |
| Design System Creation | 34 components | 40 | New tokens, component library, responsive framework |
| Template Development | 18 templates | 45 | EDS page templates with block definitions |
| Standard Block Development | 20 blocks (Low-Med) | 30 | Cards, heroes, accordions, navigation |
| Complex Block Development | 14 blocks (High) | 70 | Forms, wizards, tools, pharmacy flows |
| Integration Layer | 20 integrations | 60 | Edge workers, API proxies, third-party connections |
| Content Migration - Automated | 131 pages | 15 | Scripted migration with validation |
| Content Migration - Manual | 230 pages | 80 | Manual creation and QA |
| Localization (Spanish) | 8 pages + framework | 10 | i18n framework + content |
| QA & Testing | All | 50 | Cross-browser, accessibility, integration testing |
| Performance Optimization | All | 10 | Lighthouse 100, CWV optimization |
| UAT & Stakeholder Review | All | 15 | Business validation cycles |
| Documentation & Training | - | 10 | Author guides, developer docs |
| TOTAL |  | 535 |  |

## 10.2 Phase Summary

| Phase | Effort (Person-Days) | Duration (Weeks) | Team Size |
| --- | --- | --- | --- |
| Phase 1: Design & Architecture | 85 | 6 | 3 |
| Phase 2: Core Development | 170 | 10 | 4 |
| Phase 3: Integration & Complex Features | 130 | 8 | 4 |
| Phase 4: Content Migration | 95 | 6 | 3 |
| Phase 5: QA, UAT & Launch | 55 | 4 | 3 |
| TOTAL | 535 person-days | ~34 weeks | 4 avg |

## 10.3 Cost Estimate (Blended Rate)

| Resource | Rate/Day | Days | Cost |
| --- | --- | --- | --- |
| Solution Architect | $1,800 | 40 | $72,000 |
| Senior Frontend Developer (x2) | $1,500 | 200 | $300,000 |
| Integration Developer | $1,600 | 100 | $160,000 |
| UX/Design Lead | $1,400 | 50 | $70,000 |
| Content Migration Specialist | $1,000 | 80 | $80,000 |
| QA Engineer | $1,200 | 50 | $60,000 |
| Project Management | $1,400 | 34 weeks | $47,600 |
| TOTAL ESTIMATED COST |  |  | ~$789,600 |

# 11. Recommendations

Migration Strategy:

1. Phased approach - Start with static content to establish patterns, then tackle interactive tools

2. Edge Worker architecture - Critical for Coverage Check, Pharmacy, and Savings Card workflows

3. Microservice layer - Required for pharmacy platform (3-vendor integration) and insurance verification

4. Design system first - Establish component library before content migration

5. HCP site separation - Treat as distinct workstream with shared design tokens

Critical Path Items:

• Insurance payer API access and documentation (blocking 32 pages)

• ConnectiveRx/SS&C Health integration docs (blocking 44 pages)

• CoAssist/AssistRx pharmacy API access (blocking 13 pages)

• CoverMyMeds partnership agreement for EDS (blocking 5 pages)

# Appendix A: Asset Inventory

| Asset Type | Estimated Count | Source |
| --- | --- | --- |
| Product logos/brand assets | ~30 | /content/dam/novonordisk/novocare/Logos/ |
| Icon library (SVG) | ~50 | /content/dam/novonordisk/novocare/icons/ |
| Hero/banner images | ~40 | /content/dam/novonordisk/novocare/slabs/ |
| Character illustrations | ~20 | Educational section assets |
| PDF documents (PI, Med Guides) | ~30 | novo-pi.com (external) |
| Product photography | ~25 | Product pages |
| Total Digital Assets | ~195 |  |

# Appendix B: Risk Factors

| Risk | Impact | Probability | Mitigation |
| --- | --- | --- | --- |
| Payer API documentation delays | +4 weeks | High | Early vendor engagement |
| Pharmacy vendor API changes | +3 weeks | Medium | Contract API versioning |
| Regulatory content review cycles | +2 weeks | High | Parallel legal review |
| Spanish content expansion | +2 weeks | Medium | Modular i18n framework |
| Design iterations beyond scope | +3 weeks | Medium | Design sprints, early sign-off |